| REPORT FOR: | CABINET |
| --- | --- |
| Date: | 13 December 2012 |
| Subject: | Revenue and Capital Monitoring for Quarter 2 as at 30 September 2012 |
| Key Decision: | Yes |
| Responsible Officer: | Julie Alderson, Corporate Director of Resources |
| Portfolio Holder: | Councillor Sachin Shah, Portfolio Holder for Finance |
| Exempt: | No |
| Decision subject to Call-in: | Yes |
| Enclosures: | Appendix 1 - Revenue Directorates Summary Appendix 2 - Capital Monitoring Appendix 3 - Debt Management |

Section 1 – Summary and Recommendations

This report sets out the Council’s revenue and capital monitoring position as at 30 September 2012: Recommendations: Note the revenue and capital forecast outturn position at the end of September 2012; and Approve the capital virements detailed in paragraph 36. Reason (for recommendation) To present the forecast financial position and actions required to be taken.

# Section 2 – Report

Executive Summary

- The Quarter 2 Revenue and Capital financial monitoring is reporting some early identified risks to the revenue outturn position which come to £0.393m as set out at Table 1 of the main report.  These mostly arise in the Resources Directorate, in Community, Health and Wellbeing Directorate and Environment and Enterprise Directorate and therefore the directors in these areas are where possible developing detailed actions to combat and reduce the pressures.  In addition all the directorates are working towards managing and containing the financial pressure by ensuring that any discretionary spend is only incurred if it is absolutely necessary and additional approval processes are in place in respect of recruitment.

- A spending protocol has been issued in November 2012 to restrain all non-essential spend.  The Council is now targeting a deliberate under spend where this is achievable without directly impacting on front line service delivery, to help prepare for the additional pressures and the investment in change /savings going forward.

- The Final Revenue Budget and Medium Term Financial Strategy (MTFS) 2012-13 to 2014-15 report to the February 9th Cabinet set out the budgetary risks facing the Council and the directorates. This made clear that the Council’s budget will be under threat from the effects of the recession, the increase in the number of benefit claimants, continuing demographic pressures and increasing homelessness through higher rents and the introduction of the housing benefit cap.  Whilst the budget and MTFS has been increased to address these issues through growth for: demography in Adults and Children’s Services; homelessness and the impact on Bed and Breakfast; the impact of landfill tax on waste disposal costs; and to reduce historic pressures on income from trade waste and parking enforcement, which have been reducing due to economic pressure, it will still be a challenge to manage and contain all of the complex issues which arise in year.

- The opportunity was taken to address some pressures such as the new responsibilities for Public Health and summer youth projects that emerged after the Budget and MTFS was adopted, as part of the agreed outturn position presented to the June 20th Cabinet, where it was agreed to carry forward £2.7m, of which £1.2m was designated to address some of these budget pressures. However, it was not possible to fund all of the calls for carry forward and these will need to be contained within available budgets and earmarked reserves.  The Transformation and Priority Initiatives Fund (TPIF) stands at £1.184m and will provide capacity for invest to save and innovation in year.

- The format of the revenue and capital monitoring is being improved as an integral part of the Finance Transformation Plan.  The main issues for the directorates in respect of budgetary and service performance are included in the main report and Appendix 1 shows the movement in the budget from the original budget agreed at Council.

Introduction

- The total projected outturn for the Council at the end of Quarter 2 is £173.506m against the approved budget of £173.113m which represents a projected over spend of £0.393m, a 0.2% variation to budget.

Table 1 below summarises the position:

Directorates’ Position

Resources

- The position within the Resources Directorate has improved from previous quarter resulting in a net pressure of £0.134m at quarter 2.  This improvement has resulted from the action plan implemented by management to contain the pressures.  In addition to the net pressure there is a risk (not included in the forecast) of up to £70km with regard to increased postage costs within the Post Room Service and further work is being undertaken to clarify and address this.

- Additional procurement staffing costs due to delay in implementing new structure have been offset by an additional procurement savings from the successful outcome of a contract dispute.

- Risk around possibility of Transport For London (TFL) requesting 2011-12 Concessionary Fares savings amounting to £0.172m be retained by them was reported at quarter 1.  This was vigorously resisted by Harrow and the other 8 boroughs involved and confirmation has now been received from TFL that they will not be pursuing recovery of this funding.

- Under the new structure, Corporate Finance is now part of Resource Directorate, however for now still using the old directorate structure.

- The main projected variances and risks are set out below:

  - The former Corporate Finance Directorate is projecting a net under spend of £0.189m resulting from Contributions and Levies savings (£22k), various under spends across the directorate and favourable balance on GRIR account £77k.  This is offset by budget pressure on staffing costs within Benefits (£91k) as a result of the Council Tax Support scheme implementation;

  - The former Assistant Chief Executive’s Directorate is projecting a net over spend of £52k.  This includes the corporate pressure of £0.215m in relation to Learning and Development commissioning (£60k), Cross Cutting Efficiencies (£0.100m), merger of Policy and Partnership teams (£21k) and delays in implementation of Performance Management Business case (£34k).  The corporate pressure is reduced by various net under spends across the directorate; and

  - Legal and Governance Services is projecting an over spend of £0.271m resulting from delays in establishing the shared service with Barnet (£0.100m), under recovery of income from citizenship ceremonies (£51k) and cost in relation to increase in volume of child protection cases (£0.120m).

Community Health and Wellbeing

- The Directorate is projecting an over spend of £0.446m, which is a moderate increase from the previous quarter.  The decline in position is principally due to increased pressures on the Housing Needs budget, both in respect of an increasing number of households in bed and breakfast accommodation and under achievement of net income in respect of Private Sector Leases. If this trend continues, there may need to be a call on the general contingency.

- Significant variances are highlighted below:-

- Adult Services are forecasting an over spend of £0.110m which is mainly due to Harrow’s share of over spends on Central & North West London Foundation Trust;

- Community and Culture are reporting an adverse variance of £0.270m.  This principally relates to a shortfall on leisure centre income (£0.212m) and under achievement of MTFS savings on libraries (£0.100m).  Mitigation includes ongoing work to maximise income, vacancy management, cost management on major contracts, essential spending only and identify procurement savings;

- Currently, Housing Services are reporting an over spend on General Fund services of £24k. This is mainly due to increased pressures on the Housing Needs budget, both in respect of an increasing number of households in bed and breakfast accommodation and under achievement of net income in respect of Private Sector Lease; and

- There is a projected over spend of £42k in respect of performance support costs falling on the Department following the merger of the Adults and Housing Directorate with Community and Culture Directorate.

- Public Health

  - The Council is continuing to progress the transfer of Public Health services to the Council from April 2013 in line with the agreed transition plan. Costs associated with transition are expected to be in the region of £0.356m.  This will be partly funded from the carry forward of £0.114m which was approved as part of the 2011-12 outturn and partly from the allocation received from the Department of Health (£83k).  This therefore indicates a potential overspend of £0.159m, although there may be scope to charge some of these costs to capital.

  - Harrow and Barnet Councils have agreed in principle to share Public Health Services with Harrow as the host borough.  This is subject to the authorities signing a legal agreement and agreeing an operating model.

Environment

- Environment and Place Shaping Directorates are shown separately but has become one Directorate in quarter 3.

- The directorate is forecasting an adverse variance of £0.194m.  The forecast position has declined significantly since quarter 1.  The main change is due to supplementary call on the levy from West London Waste Authority to reduce their budget deficit, which is offset by rebate from Pay As You Throw (PAYT) costs resulting in net additional levy of £0.290m.  In addition, the income target for dry recyclables is not achievable due to volatile market price for the profit share element resulting in an adverse variance of £0.317m.  This is offset by drop in adverse variance for parking enforcement income due to improvement in activity and capturing new areas of enforcement as part of partnership work with police to address crime disorder and to compliment traffic management policies.

- In addition, Property and Infrastructure is also showing a favourable variance of £0.258m which is mainly due to additional SLA income, Depot rental income, Civic Centre parking income, Street Works income and forecast income for Major Works in respect of capital re-charges offset by £85k MTFS saving in respect of Property Repairs and Maintenance Procurement Value Chain which is not likely to materialise.

- The directorate management is forecasting an under spend of £32k resulting from vacancy which is offset by recruitment costs.

- Adverse variance of £0.202m in Public Realm Services mainly results from under achieving the income target for dry recyclables due to the volatile market price for the profit share element.  Some of the pressure has been eliminated with the new contract from September 2012 and vacancy management.

Children’s and Families

- The directorate is forecasting a favourable net variance of £19k.  Majority of the favourable variances are from vacancy management (£0.257m) and staff savings (£66k) resulting from the New Operating Model.

- This is offset by forecast overspend of £0.304m on Targeted Services mainly due to Interim cover for Divisional Director (£64k), Placement services (£0.138m) for children looked after, leaving care and unaccompanied asylum seeker children; and Staffing budget for Children in Need and Children’s Access Teams.

Place Shaping

- The forecast outturn position indicates a minor overspend mainly resulting from Planning fee income (£0.188m) due to changes in permitted development rights and planning appeal costs (£34k).  This is offset by salary savings and increase in corporate estate rental income (£0.188m).

Capital Financing

- The forecast outturn at quarter 2 is a favourable variance of £0.371m which has improved by £0.188m since quarter 1.  This has resulted from the changes in the Treasury Management lending strategy, to take advantage of higher longer term rates on loans offered by government backed banks, adopted by the Council in February 2012.

Carry Forwards

- The Cabinet approved revenue carry forwards of £2.696m as part of the 2011-12 outturn position agreed at the 20 June Cabinet.  There are also brought forward balances on the Local Authority Area (LAA) Grant and the Local Planning Development Grant (LPD) of £0.705m. As at quarter 2 £1.553m were released to the directorates which leaves a balance of £1.143m remaining to be allocated to the directorates and will be allocated as it is required, rather than in advance of need. The forecast assumes that all of the carry forwards will be allocated in year.

Housing Revenue Account (HRA)

- The forecast outturn at quarter 2 is an over spend of £0.106m which results into forecast surplus for the year of £0.677m against a budget of £0.783m. The main variance comes from a forecast decrease in service charges income from leaseholders and overspends on repairs.  This is partly offset by projected under spends on capital financing cost resulting from lower capital spend in 2011-12.

Procurement and Commercialisation Efficiency Savings

- There are no central procurement savings but over £2m procurement savings are built into the MTFS Directorate efficiency plans in 2012-13.  The procurement team is assisting the delivery of these savings through the projects detailed below:-

- The print contract has been awarded to the new supplier and the MTFS savings for current year of £0.100m has been achieved.  In addition significant savings have been identified for the following year which is being incorporated into the 2013-14 budgets.

- A new contract is in place from September 2012 for dry recyclables income which will contribute to the procurement savings.  However, the savings in respect of corporate property repairs and maintenance is not likely to materialise and has been reported in the forecast outturn position.

- Work is ongoing on leisure and library services to identify potential savings.

- Major projects within the Adults services which include contract management, WLA joint procurement for residential care and supporting people are on track to achieve the target savings.

- Children’s and Families Directorate are on track to achieve majority of their procurement savings.  Work is ongoing to ensure all the savings are achieved

- The Commercialisation project is focussed on achieving the Special Needs Transport III project saving which is £0.500m in 2014-15.  Additionally there is a cross cutting target of £0.100m in the 2012-13 budget to be delivered by the Directorates aided by the Commercialisation interim manager.

Transformation and Priority Initiatives Fund (TPIF)

- The balance on the TPIF approved by the Cabinet at its meeting of 20th June as part of the outturn position was £1.184m.  No bids have been agreed for the first two quarters of the year.

Contingency

- The Contingency budget stands at £1m.  There are no anticipated calls against the Contingency as at Quarter 2. However if homelessness does rise at a rate above the current budget provision, there may need to be a call on the contingency later in the year.

Debt Management

- The latest position on Council Tax shows a potential surplus on the bad debt provision of £0.570m.  The position will be monitored closely over the next quarter and any significant changes in the bad debt provision requirement will be taken into account for the budget setting process for 2013-14.

- National Non Domestic Rates collection shows a potential overprovision of £0.371m.  This position will be closely monitored.  There is no direct financial impact on the Council as business rates are a call on the national non-domestic rate pool of central government.

- The arrears on Housing Benefits show a potential increase in the Bad Debt Provision of £0.562m which will be will be partly funded from improved collection and additional subsidy payments.  There is a potential risk of adequate funding of the provision which will be closely monitored and will be incorporated as part of quarter 3 forecast outturn position.

- The PCT are challenging their contribution to continuing care costs for both children’s and adults. Consequently the PCT debt for both totals to approximately £3.400m as at 30 September 2012.  The position with the PCT debt poses a significant financial risk which has not been factored into the quarter 2 forecast outturn as the negotiations are on going.

Capital Programme

- The approved gross Capital Programme at February 16 Council was £43m in 2012-13 and £66m in future years. £18.7m was approved in carry forwards as part of the 2011-12 outturn by the Cabinet at their 20 June meeting, increasing the overall programme to £61.7m. The projected under spend at quarter 2 is £13.8m which is an increase of £5.5m from the previous quarter. Main areas of significant under spends are detailed below:-

  - Children’s Directorate is forecasting a slippage of £9.188m resulting mainly from :-

    - Delays on the Schools Expansion Programme (£7.3m) for Vaughan and Marlborough Primary Schools due to extensive development and consultation phase and ongoing discussion with DfE in respect of bringing forward the Priority School Building (PSB) programme funding; and

    - The major refurbishment programme for Weald Infant and Junior school (£1.3m) has been put on hold as a result of the schools inclusion in the DfE's PSB programme.

  - The DfE have confirmed an additional allocation of Basic Need Capital Grant to fund the capital cost of pupil growth totalling £2.64m.  This will be applied to fund the approved primary school expansion programme thereby reducing the total funding that would have been required from the Council.

  - The total under spend within the Community, Health & Wellbeing Directorate is £1.780m resulting mainly from

    - Disabled Facilities and Empty/Better Homes grants (£0.398m);

    - Adults Services are projecting a slippage on Milman's Centre (£0.186m), HIV Supported Housing scheme (£0.352m) and Bentley Reablement Centre project (£0.227m); and

    - Cultural services are anticipating a slippage on both Headstone Manor (£0.300m) and Harrow Museum (£0.250m) programme as awaiting decision for lottery funding.

  - The Resources directorate are forecasting a slippage on the ITO project (£0.768m) mainly resulting from changes in delivery date for Local Area Network (LAN) and Citrix application projects.  Further requirements have been identified for refreshing Laptops and Windows 7 compatibility application which will run across two years (2012/13 and 2013/14).  An update on the cost and funding of this will be reported at quarter 3.

  - Place Shaping directorate are anticipating a slippage of £2.050m resulting mainly from projects for St Ann’s & Kymberley Road (£1m), Pinner Park Farm (£0.200m), Strategic Sites Project (£0.500m) and Asset Development Projects (£0.250m).

- The HRA programme currently estimates an under spend of £1.050m compared to the revised programme.

- One off virements are recommended as detailed in the table below:

| Description | From | To |
| --- | --- | --- |
|  | £000 | £000 |
| Adult Social Care Framework I project |  | 250 |
| Supported Housing (HIV) | 250 |  |
| St. Ann’s Road project |  | 500 |
| Strategic Sites | 500 |  |
| Total | 750 | 750 |

Financial Implications

- Financial matters are integral to the report.

## Environmental Impact

- There are none directly related to this report.

Performance Issues

- Good financial performance is essential to achieving a balanced budget.  The financial performance is integrated with the strategic performance of the Council through quarterly Improvement Boards for each Directorate where the financial position is considered at the same time as performance against key projects, service KPIs (including customer data and complaints) and workforce. Monitoring of finance and performance is reported regularly to the Corporate Strategic Board and Cabinet and is also considered by the Council's Performance and Finance Scrutiny Sub- Committee.

Risk Management Implications

- The risks to the council and how they are being managed are clearly set out in the report:

Risks included on Directorate risk registers? Yes

Equalities Implications

- There are no direct equalities impacts arising from the decisions within this report.

Corporate Priorities

- This report deals with the Revenue and Capital monitoring which is key to delivering the Council’s corporate priorities.

Section 3 - Statutory Officer Clearance

| Name: Julie Alderson | √ |  | Chief Financial Officer |
| --- | --- | --- | --- |
| Date: 22 November 2012 |  |  |  |
|  |  |  | on behalf of the |
| Name: Matthew Adams | √ |  | Monitoring Officer |
| Date: 3 December 2012 |  |  |  |

# Section 4 – Performance Officer Clearance

|  |  |  | on behalf of the |
| --- | --- | --- | --- |
| Name: Liz Defries | √ |  | Divisional Director Strategic Commissioning |
| Date: 19 November 2012 |  |  | Partnership, Development and Performance |

# Section 5 – Environmental Impact Officer Clearance

| Name: John Edwards | √ |  | Divisional Director |
| --- | --- | --- | --- |
| Date: 16th November 2012 |  |  | (Environmental Services) |

# Section 6 - Contact Details and Background Papers

Contact:  Julie Alderson Email: julie.alderson@harrow.gov.uk

Background Papers: https://www.harrow.gov.uk/www2/ieListDocuments.aspx?CId=249&MId=60645&Ver=4

| Call-In Waived by the Chairman of Overview and Scrutiny Committee |  | NOT APPLICABLE [Call –in applies] |
| --- | --- | --- |

# Consolidated

Resources

Environment

Community, Health and Wellbeing

Children’s Services

Place Shaping

HRA

Council Tax

Currently, bad debt provisions (BDP) of £3.892m exist [£4.142m- £0.250m; w/offs done 01/04/12-30/09/12] for Council Tax against a potential BDP of £3.322m for debts accrued to 31 March 2012.

| COUNCIL TAX | Arrears as at 1st of April | Arrears as at Qtr 2 | BDP | BDP as at Qtr 2 |
| --- | --- | --- | --- | --- |
|  | £000 | £000 | % | £000 |
| Pre 2008-2009 | 834 | 732 | 100 | 732 |
| 2008-2009 | 643 | 557 | 100 | 557 |
| 2009-2010 | 816 | 714 | 75 | 536 |
| 2010-2011 | 1,264 | 1,113 | 60 | 668 |
| 2011-2012 | 2,193 | 1,658 | 50 | 829 |
| Total | 5,750 | 4,774 |  | 3,322 |

National Non Domestic Rates (NNDR)

Currently, bad debt provisions of £2.288m [£2.500m- £0.212m; w/offs done 01/04/12 to 30/09/12] exist for business rates (NNDR) against a potential BDP of £1.917m. But as the business rates are a call on the national non-domestic rate pool of central government there is no financial affect to this Authority.

| NATIONAL NON DOMESTIC RATES (NNDR) | Arrears as at 1st of April | Arrears as at Qtr 2 | BDP | BDPas at Qtr 2 |
| --- | --- | --- | --- | --- |
|  | £000 | £000 | % | £000 |
| Pre 2011-2012 | 1,237 | 969 | 100 | 969 |
| 2011-2012 | 1,608 | 1,265 | 75 | 948 |
| Total | 2,845 | 2,234 |  | 1,917 |

Council Tax and Business Rates Court Cost

Currently, bad debt provisions (BDP) of £0.845m exists for Court Costs against a potential BDP of £0.917m.  From previous years trends, this amount of provision appears to be adequate and in line with our overall provisions policy.

| Court Cost | Arrears as at 1st of April | Arrears as at Qtr 2 | BDP | BDP as at Qtr 2 |
| --- | --- | --- | --- | --- |
|  | £000 | £000 | % | £000 |
| Pre 2009-2010 | 277 | 235 | 100 | 235 |
| 2009-2010 | 163 | 141 | 85 | 120 |
| 2010-2011 | 247 | 205 | 75 | 154 |
| 2011-2012 | 450 | 338 | 60 | 203 |
| 2012-2013 | 0 | 410 | 50 | 205 |
| Total | 1,137 | 1,329 |  | 917 |

Housing Benefits

Currently, bad debt provisions of £2.024m [£2.119m - £0.095m w/offs 1/4/12 to 30/09/12] exist for Housing Benefit overpayment debt against a potential BDP of £2.586m (£1.829m+£0.757m).  The under provision will be partly funded from improved collection and additional subsidy payments.

| Housing Benefit DEBTORS | Outstand as at 1st of April | Outstand as at Qtr 2 | BDP | BDP as at Qtr 2 |
| --- | --- | --- | --- | --- |
|  | £000 | £000 | % | £000 |
| Pre 2010-2011 | 875 | 736 | 100 | 736 |
| 2010-2011 | 520 | 393 | 100 | 393 |
| 2011-2012 | 1,253 | 768 | 50 | 384 |
| 2012-2013 | 0 | 1,055 | 30 | 316 |
| Totals | 2,648* | 2,952 |  | 1,829 |

| Housing Benefit LIVE CASES | Outstand as at 1st of April | Outstand as at Qtr 2 | BDP | BDP as at Qtr 2 |
| --- | --- | --- | --- | --- |
|  | £000 | £000 | % | £000 |
| Pre 2010-2011 | 264 | 162 | 100 | 162 |
| 2010-2011 | 429 | 261 | 75 | 196 |
| 2011-2012 | 1,181 | 702 | 30 | 210 |
| 2012-2013 | 0 | 943 | 20 | 189 |
| Totals | 1,874 | 2,068 |  | 757 |

*The arrears as at 30/9/12 were a combination of closed accounts (debtors) and live cases. However, in order to obtain a more realistic bad debt provision we have this year separated the two areas as the risk of non collection is very different for the two areas, the former being owed by clients who no longer receive benefits or have moved out of the borough, and the latter relating to clients currently residing in Harrow and claiming housing or council tax benefits. Re this category, we can attach benefits to offset against debts and obtain payment direct from the DWP which reduces non collection risk. The DPD rates applied reflect this situation.

Housing Revenue Account

This provision represents Leasehold Service Charge and Major Works, Current and Former tenants’ rents and Garages and Commercial rents arrears. Within the HRA an annual contribution of £0.200m is budgeted to support any changes in the required level of provision.

Current provision of £0.409m exist, after allowing for estimated write offs amounting to £0.229m.  The estimated requirement as at quarter 2 is £0.553m which suggest an increase of £0.144m.

Debt Summary

|  | Rent | Leasehold |  |  |
| --- | --- | --- | --- | --- |
| £’000 | Current tenants | Former tenants | Garages | Service charges | Major Works | Shops & Commercial | Total Debt |
| Gross debt @ 01/04/2012 | 467 | 727 | 31 | 128 | 20 | 108 | 1,461 |
| Debt at 30/09/2012 |  |  |  |  |  |  |  |
| Less than 30 days | 180 | 42 | 0 | 315 | 0 | 72 | 609 |
| 30 to 60 days | 117 | 9 | 0 | 0 | 0 | 0 | 126 |
| 60 to 90 days | 38 | 3 | 36 | 0 | 0 | 0 | 77 |
| 90 to 180 days | 68 | 16 | 0 | 0 | 0 | 25 | 109 |
| 181 to 365 days | 37 | 48 | 0 | 42 | 2 | 19 | 148 |
| > 365 days | 6 | 618 | 0 | 42 | 11 | 24 | 701 |
| Debt @ 30/09/2012 | 446 | 736 | 36 | 399 | 13 | 140 | 1770 |
| Bad Debt Provision |  |  |  |  |  |  |  |
| Opening bad debt provision @ 01/04/2012 | 0 | (638) | 0 | 0 | 0 | 0 | (638) |
| Write offs to date | 0 | 32 | 0 | 0 | 0 | 0 | 32 |
| Estimated further write offs | 0 | 122 | 25 | 40 | 10 | 0 | 197 |
| Total estimated write offs to year end | 0 | 154 | 25 | 40 | 10 | 0 | 229 |
| Current bad debt provision after write offs @ 31/03/2013 | 0 | (484) | 25 | 40 | 10 | 0 | (409) |
| Bad debt provision required@31/03/2013 | 0 | (553) | 0 | 0 | 0 | 0 | (553) |
| Revenue contribution to top up provision | 0 | (69) | (25) | (40) | (10) | 0 | (144) |