| REPORT FOR: | OVERVIEW AND SCRUTINY COMMITTEE |
| --- | --- |
| Date of Meeting: | 17th September 2013 |
| Subject: | Scrutiny Work Programme Update |
| Responsible Officer: | Alex Dewsnap Divisional Director, Strategic Commissioning |
| Scrutiny Lead Member area: | All |
| Exempt: | No |
| Enclosures: | None |

Section 1 – Summary and Recommendations

This report provides Members with an update on the projects currently underway as part of the scrutiny work programme Recommendations: Councillors are asked to: Note the progress on the individual projects Note the timetable for completion of projects Agree proposals for identifying any further projects for inclusion in the work programme

# Section 2 – Report

A number of detailed scrutiny review projects are currently underway.  This report provides members of the Overview and Scrutiny committee with an update on each of these projects.

2.1	Current Projects

The projects as set out below are currently underway or are about to commence:

Standing Scrutiny Review of the Budget

It had originally been proposed that this project would review the following areas over the coming months:

- Response to the Business Rate Retention scheme will be considered during 2013

- Fees and charges will be considered during 2013

- Following discussions at the Scrutiny Leadership Group, the budget review also intends to consider the cost of transition from child to adult disability services

However, the membership of the project has now significantly changed and as such a further meeting will be needed to confirm the focus of the project for the remainder of this administration.

Regular reports are submitted to both the Overview and Scrutiny Committee and, where necessary, Cabinet.  A final report, summarising the work of the standing review during the course of this administration will be presented to the Overview and Scrutiny committee in January 2014

Customer Care

The report from this project has now been drafted and is subject to consultation with review group members.  Project work has included visits to other boroughs, experience of front line customer services and focus groups with staff.  The final report and recommendations are likely to be submitted to the Overview and Scrutiny in October 2013.

Accessible Transport

This project has investigated the impact of poor accessibility to public transport on the life experiences of residents. It has gathered information of the experiences of residents through a seminar, public consultation and journeys through the borough alongside residents with disabilities. The issues identified have now been discussed with council officers and TfL.  The final report and recommendations are included elsewhere on the agenda for this meeting.

NW London Joint Health Overview and Scrutiny Committee (JHOSC) – Shaping a Healthier Future

The JHOSC met on 3rd September 2013 and Members will considered how to monitor the implementation of Shaping A Healthier Future proposals.  The meeting agreed that there will be components of the Shaping a Healthier Future programme upon which individual boroughs will which to make individual comments and representations via there own scrutiny functions.  However, it was also agreed that there are a number of cross borough issues upon which the JHOSC offers an important opportunity for collective discussions and sharing of information/concerns between boroughs.  It was therefore agreed that the JHOSC will continue to meet with an agreed, specific work programme.  The next meeting has been scheduled for 3rd December.

NHS Health Checks

This is a joint review between Harrow and Barnet which will look at the role of the Council’s Public Health team having effective arrangements in place for NHS Health Checks.   This project is in the initial scoping stages.

Mental Health

The Chair and Vice Chair of the Health and Social Care Scrutiny Sub-Committee are committed to looking at mental health services in more detail and are currently considering how best to take this work forward.

2.2	Future Projects

Given the Local Government elections in May 2014 and the implementation of the period of purdah on council activities, the Scrutiny Leadership Group has agreed that all projects will be completed and presented to Cabinet for decision early in 2014.  At this time, it is anticipated that the work programme between now and the end of the year will therefore comprise:

- Standing Review of the Budget

- Child’s Journey Through Care

- NHS Health Checks

- Potential ongoing work with the JHOSC

Should the Scrutiny Leadership Group identify any further projects it wishes to undertake within this timeframe, these will be assessed against the criteria below and also the likelihood of their being completed within the agreed timeframe.

- Cross party engagement achievable among scrutiny Members

- Capacity to influence (add value to decision making)

- Scope to improve financial/service performance

- Community relevance (potential to impact whole borough - demographically or geographically)

- Addresses future policy requirements

- Party political neutrality – especially important. in run up to next election

- Resource from the scrutiny team to support the project

## Financial Implications

There are none associated with this report.

## Performance Issues

There are none associated with this report.

## Environmental Impact

There is none associated with this report.

## Risk Management Implications

There are none associated with this report.

#### Equalities implications

An equalities impact assessment has not been undertaken in relation to this report as it makes no proposals with regard to service change

## Corporate Priorities

All

# Section 3 - Statutory Officer Clearance

Not required for this report.

# Section 4 - Contact Details and Background Papers

Contact:  Lynne Margetts, Service Manager Scrutiny 020 8420 9387

lynne.margetts@harow.gov.uk

Background Papers:

None