CABINET - 12 DECEMBER 2013

PROGRESS ON SCRUTINY PROJECTS

| Review | Methodology | Type of report | Expected date for report to Cabinet | Comments |
| --- | --- | --- | --- | --- |
| Standing Review of the Budget | Standing Review | Regular update reports to O&S and interim, specific topic and final reports to O&S and Cabinet | A report from the review’s consideration of the use of capital has been drafted. | Evidence gathered during the lifetime of the project will be used to inform the Question and Answer session on the budget in January 2014. It is unlikely that further projects will be undertaken before the next election, however a final report will be prepared for the Overview and Scrutiny committee in February 2014 |
| Customer Care | Light touch review | Final Report to O&S and Cabinet | January 2014 | The report will be presented to the Overview and Scrutiny committee on 17th December. |
| Accessible Transport | Light touch review | Final Report to O&S and Cabinet with reference to Transport for London | Received in October 2013 Response from officers November 2013 | This project is complete |
| NHS Health Checks – supported by Centre for Public Scrutiny (CfPS) | Joint light touch review with Barnet | Final Report to O&S/Health and Social Care sub committee and Cabinet | Estimated February/March 2014 | This is a joint review between Harrow and Barnet which will look at the role of the Council having effective arrangements in place for NHS Health Checks. A draft report from the project is being prepared for consideration by both groups. Because of the timing of the Question and Answer session on the budget in January, there may be a delay in submitting the report to committee |
| Joint Overview and Scrutiny Committee ‘Shaping a Healthier Future’ | Joint Committee | Update reports will be provided for O&S/Health and Social Care sub committee and Cabinet (for information) | As required | At the last meeting of the joint committee in September councillors from across the seven boroughs agreed to continue meeting to consider the ongoing implementation of the Shaping a Healthier Future proposals – it is anticipated that full implementation will take up to 5 years though the downgrading of A&E departments at Central Middlesex and Ealing hospitals has been announced. The implications of these changes on the capacity of Northwick Park has been identified as an area of concern by councillors, particularly if they go ahead before improvements have been made to Northwick Park A&E. Councillors are investigating the timetabling of the changes. The next meeting of the Joint Committee took place on 3rd December 2013. |
| Deletion of Chief Executive post | Challenge panel | Final report to O&S and the Leader of the Council | January 2014 | The Scrutiny Leadership Group wishes to contribute to the Leader’s consultation on the proposed deletion of the Chief Executive post. The challenge panel took place on 4th December and a report will be prepared for the Overview and Scrutiny committee as soon as possible. |
| Child’s Journey Through Care | Light touch review | Final Report to O&S and Cabinet | TBC | This review has been postponed but councillors have asked that it remains on the scrutiny work programme |

All scrutiny projects will be completed and reported through to cabinet as early as possible in 2014.

Contact: Lynne Margetts, Service Manager Scrutiny, 020 8420 9387