CABINET – 15 JANUARY 2014

PROGRESS ON SCRUTINY PROJECTS

| Review | Methodology | Type of report | Expected date for report to Cabinet | Comments |
| --- | --- | --- | --- | --- |
| Standing Review of the Budget | Standing Review | Regular update reports to O&S and interim, specific topic and final reports to O&S and Cabinet | A report from the review’s consideration of the use of capital has been drafted. | Evidence gathered during the lifetime of the project will be used to inform the Question and Answer session on the budget in January 2014. No further projects will be undertaken before the next election, however a final report will be prepared for the Overview and Scrutiny committee in February 2014 |
| Customer Care | Light touch review | Final Report to O&S and Cabinet | January 2014 | The report was agreed by the Overview and Scrutiny committee on 17th December. It will be received by Cabinet in January and responded to in February. |
| Accessible Transport | This project is complete |
| NHS Health Checks | Joint light touch review with Barnet | Final Report to O&S/Health and Social Care sub committee and Cabinet | Estimated February/March 2014 | This is a joint review between Harrow and Barnet which has considered the arrangements in place for NHS Health Checks. A draft report from the project is being prepared for consideration by both boroughs. Because of the timing of the Question and Answer session on the budget in January, there may be a delay in submitting the report to committee |
| Joint Overview and Scrutiny Committee ‘Shaping a Healthier Future’ | Joint Committee | Update reports will be provided for O&S/Health and Social Care sub committee and Cabinet (for information) | As required | The Joint Committee met on 3rd December 2013. It will continue to meet to monitor the implementation of the proposals from ‘Shaping a Healthier Future’ |
| Deletion of Chief Executive post | Challenge panel | Final report to O&S and the Leader of the Council | January 2014 | The challenge panel took place on 4th December and a special meeting of Overview and Scrutiny committee on 8th January 2014 will consider the report from this challenge panel. |
| Child’s Journey Through Care | Postponed but included in the scrutiny work programme 2014/15 |

All scrutiny projects will be completed and reported through to cabinet as early as possible in 2014.

Contact: Lynne Margetts, Service Manager Scrutiny, 020 8420 9387