## School Expansion Board
Annexe A - School Expansion Programme indicative capital costs - Cabinet report 15 January 2014
Project\Financial Year | Original Pre-feasibility Estimated Project Cost | Spend to date | Current Post-feasibility Forecast | Variance to Original Estimated Project Cost | Scheme | Note
LAST UPDATED: | Aug 2013 | Dec 2013 | Dec 2013
SEP Phase 1
Marlborough (£10,500) | 4900 | 409.185 | 2150 | -2750 | PSBP | 1
Vaughan (£8,500) | 2900 | 356.934 | 2900 | 0 | PSBP | 1
Pinner Parks | 2850 | 253.816 | 3100 | 250 |  | 2
Stanburn | 2150 | 1038.762 | 2150 | 0
Glebe | 1750 | 1235.686 | 1750 | 0
Camrose | 297 |  | 297 | 0
Cedars Manor | 26 |  | 26 | 0 | PSBP
TOTAL SEP Phase 1 | 14873 | 3294.383 | 12373 | -2500
SEP Phase 2 Group 1 (Sep 14 Expansions)
Norbury | 2300 |  | 3000 | 700 | TBNP
Belmont | 2010 | 4.281 | 2450 | 440 | TBNP
Pinner Wood | 1000 | 13.366 | 1250 | 250
Grange | 1250 |  | 1550 | 300
Aylward | PSBP | 56.683 |  | 0 | PSBP
TOTAL SEP Phase 2 Group 1 | 6560 | 74.33 | 8250 | 1690
SEP2 Phase 2 Group 2 (Sep 14 Expansions)
St Anselm's alternative | 5100 |  | 3500 | -1600 | TBNP
St John Fisher | 2400 |  | 2850 | 450 | TBNP
Newton Farm | 2150 |  | 2950 | 800 | TBNP
Cannon Lane | 3130 | 82.398 | 3700 | 570 | TBNP
Priestmead | PSBP |  |  | 0 | PSBP
Kenmore Parks | 3500 | 50 | 3100 | -400
Whitchurches | 2010 |  | 1800 | -210 | TBNP
TOTAL SEP Phase 2 Group 2 | 18290 | 132.398 | 17900 | -390
SEP Phase 3 (assume Sep 17 expansions)
Expansion 1 | 2500 |  | 2500 | 0
Expansion 2 | 2500 |  | 2500 | 0
Expansion 3 | 2500 |  | 2500 | 0
TOTAL SEP Phase 3 | 7500 | 0 | 7500 | 0
SEN Expansions
Woodlands | 2500 | 17.595 | 2675 | 175 | TBNP
Kingsley | 2500 |  | 1100 | -1400 | TBNP
Shaftesbury | 2500 |  | 2600 | 100 | TBNP
West Lodge Mainstream Unit | 1500 |  | 950 | -550 | TBNP
St George's alternative Mainstream Unit | 1500 |  | 950 | -550 | TBNP
Bentley Wood Mainstream Unit | 1500 | 0 | 1500 | 0 | TBNP
TOTAL SEN Expansions | 12000 | 17.595 | 9775 | -2225
Secondary Expansions
Bentley Wood | 2150 |  | 2350 | 200 | TBNP
Whitefriars Community | 12400 |  | 15950 | 3550 | TBNP
Additional New School (assume Sep 19 opening)
Total Secondary Expansions | 14550 | 0 | 18300 | 3750
School Expansion programme contingency at 5% (excl SEP 1) |  | 0 | 3086.25 | 3086.25
Other
Capital Maintenance | 8100 | 2016.72 | 8100 | 0
IT | 950 | 22.85 | 950 | 0
2YO grant | 438 |  | 438 | 0
Short Breaks | 256 | 191.391 | 256 | 0
Bulge classes | 525 | 220.228 | 525 | 0
Amalgamations | 1900 | 2723.7 | 1900 | 0
TOTAL Other | 12169 | 5174.889 | 12169 | 0
TOTAL ESTIMATED SPEND | 85942 | 8693.595 | 89353.25 | 3411.25
Spreadsheet notes and assumptions
1) For Marlborough and Vaughan schemes, PSBP will deliver the schemes up to approximate £6m costs, but the council may be required to contribute to the total cost of the scheme
2) £250k funded directly by school