CORPORATE ANTI-FRAUD TEAM

SERVICE PLAN 2015-16

|  | Project Number, Name & Description | Expected Outcome | Performance Measures/Milestones | Priority Action? | By Whom (Lead) | By When | Transformation Link | Risk/ Dependency | Workforce Implications | Service L&D Implications |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Council Tax Support (CTS) Fraud | The identification of 12 positive outcomes and/or £15,000 CTS fraud identified including awareness raised within the service area | 3 positive outcomes or £3750 fraud identified per quarter |  | Justin Phillips | April 2016 | No | Sufficient referrals | None | None |
| 2. | Housing Tenancy Fraud | Identification of 12 positive outcomes of housing tenancy fraud (including RTB, succession and assignment applications) and where appropriate possession and/or criminal action sought | 3 positive outcomes identified per quarter |  | McKinley Erysthee | April 2016 | No | Sufficient referrals | None | None |
| 3. | Experian Housing Tenancy fraud data match exercise | Completion of Experian Housing Tenancy data match | All matches sifted by September 2015 and high risk cases live under investigation |  | McKinley Erysthee | Sept 2015 | No |  | None | None |
| 4. | Pan London Housing Fraud Hub | Embed the Housing Fraud Hub within Housing Needs to support front line service delivery | Use of the hub integrated into housing needs procedures and instances of housing needs/application fraud identified |  | Justin Phillips | Aug 2015 | No | IT support | None | None |
| 5. | Explore & develop MOU’s with local Registered Social Landlords | Agree MOU’s with at least 3 RSL’s to generate new work streams in relation to housing tenancy fraud | Set up regular meetings with Senior Managers at RSLs to discuss their arrangements in place to deal with housing tenancy fraud |  | McKinley Erysthee | April 2016 | No | General appetite from RSLs to partnership working | None | None |
| 6. | Blue badge fraud | Identification of 12 positive outcomes through responsive work and proactive fraud drives working with Met Police SNT’s and in conjunction with the Council’s Day of Action Programme in each quarter | Fraud drives delivered at least quarterly and reactive cases dealt with in a timely manner |  | Justin Phillips | April 2016 | No |  | None | None |
| 7. | Direct payment fraud | Identification of £50K of direct payment fraud/financial irregularity through a sample review of high risks cases including awareness raised within service area | Identification of appropriate cases and completion of review |  | Francoise Williams | April 2016 | No | Co-operation of Personalisation Team in accessing appropriate cases | None | None |
| 9. | School application fraud | Identification of school admission fraud/financial irregularity through a sample review of high risk cases provided by the admission team including awareness raised within service area | Completion of review and findings /recommendations reported to admissions |  | Justin Phillips | Sept 2015 | No | Co-operation of education | None | None |
| 10. | NFI 14/15 exercise | Supporting service areas in the timely processing of high risks matches to satisfactory conclusion | All high risk matches processed by service areas and appropriate cases referred for investigation |  | Justin Phillips | April 2016 | No | Co-operation of both internal and external agencies | None | None |
| 11. | Income opportunities/ generation | £10K income generated through administrative penalties and recovery of investigation costs | Generation of income |  | Justin Phillips | April 2016 | No | Availability of appropriate cases and subject to changes in the way this income is reflected for accounting purposes | None | None |
| 12. | Deliver fraud awareness campaign | Deliver fraud awareness campaign and co-ordinate communications prior in conjunction with International Fraud Awareness Week 15/11/15 - 21/11/15 | Raised fraud awareness internally and throughout borough |  | Justin Phillips | Nov 2015 | No |  | None | None |
| 13. | Fraud risk review of waiting list/temporary accommodation cases | Identification of fraudulent housing applications / interception of cases before permanent allocation of tenancy through sample review including raising awareness within service area | Completion of review |  | Chris Beynon | April 2016 | No | Co-operation of housing assessment /needs | None | None |
| 14. | Review and implement CIPFA Code of Practice on Managing the Risk of Fraud & Corruption | Self assess against the Code performance statements Develop action plan to meet the gaps identified Implement action plan Review progress | Self assessment complete Sept 15 Action plan drafted and submitted to GARMSC Sept/Dec 15 Action plan implementation commenced Jan 16 Review progress Jan 16 onwards |  | Justin Phillips | April 2016 | No | Co-operation internally from Service areas | None | None |

Note – Plan to be reviewed and subject to change once CIPFA self assessment work undertaken and action plan developed