Appendix 1

|  | SUBJECT | CHALLENGE PANEL ON HOMELESSNESS – DRAFT SCOPE |
| --- | --- | --- |
|  | COMMITTEE | Overview and Scrutiny |
|  | CHALLENGE PANEL | Chair – Councillor Jeff Anderson Councillors – TBC by Groups (8 members max) For information, Councillors who attended the scoping meeting are listed below: Jeff Anderson (Chair) Richard Almond Ameet Jogia Barry Kendler Barry Macleod-Cullinane Kairul Marikar Phillip O’Dell Christine Robson |
|  | AIMS/ OBJECTIVES/ OUTCOMES | To understand the drivers of homelessness in Harrow To examine whether the solutions currently being implemented effectively address these drivers To scrutinise the supply/ land/ site issues |
|  | MEASURES OF SUCCESS OF REVIEW | Recommendations to Cabinet agreed and implemented. |
|  | SCOPE | (1) to examine the drivers of homelessness in Harrow (reasons, family composition, etc.); (2) to scrutinise the effectiveness of different interventions; and (3) to scrutinise the supply/land/site issues. |
|  | SERVICE PRIORITIES | Protect the Most Vulnerable and Support Families Build a Better Harrow |
|  | CHALLENGE PANEL SPONSOR | Lynne Pennington (Divisional Director of Housing) |
|  | ACCOUNTABLE MANAGER(S) | Jon Dalton (Head of Housing Needs) Alison Pegg (Head of Housing Regeneration) Paul Nichols (Divisional Director of Planning) Tobias Goevert (Head of Regeneration and Design) Sunil Sahadevan (Head of Development Management) |
|  | SUPPORT OFFICER | Rebecka Steven |
|  | ADMINISTRATIVE SUPPORT | Policy Team |
|  | EXTERNAL INPUT | None anticipated at this stage |
|  | METHODOLOGY | A Challenge Panel will meet for 4 hours on 12 October to hear from witnesses (officers from relevant services of the Council), discuss the issues and solutions, and form recommendations. Extensive work has already been undertaken by officers on the issues raised in the scope, and a briefing will be provided to members prior to the Challenge Panel. |
|  | EQUALITY IMPLICATIONS | The Challenge Panel will during the course of its work, consider how equality implications have been taken into account in current policy and practice and consider the possible implications of any changes it recommends. In undertaking the Challenge Panel, members and officers will consider their practices and how it can ensure all relevant stakeholders in the borough to have their voices heard. |
|  | ASSUMPTIONS/ CONSTRAINTS | Timing will be the major constraint – officers are unsure as to whether the suggested scope will be able to be covered in one Challenge Panel meeting (see main report for options). |
|  | SECTION 17 IMPLICATIONS | None in terms of the scrutiny process. |
|  | TIMESCALE | Challenge Panel to take place in October, reporting to Overview and Scrutiny in November, and a referral to Cabinet thereafter if appropriate. |
|  | RESOURCE COMMITMENTS | The policy and housing teams will provide a briefing and support to the Challenge Panel. The policy team will produce the final report including recommendations to O&S; officers from the housing team (or appropriate Service) will provide a response to Cabinet and take forward any recommendations agreed by Cabinet. |
|  | REPORT AUTHOR | Rebecka Steven/ Meghan Zinkewich-Peotti |
|  | REPORTING ARRANGEMENTS | Outline of formal reporting process: The relevant Divisional Director(s) and Portfolio Holder(s) will be consulted in the drafting of the final report and recommendations Report to Overview and Scrutiny Committee Report referred to Cabinet Officer response to Cabinet |
|  | FOLLOW UP ARRANGEMENTS (proposals) | It is anticipated that Cabinet would consider any recommendations made (alongside the officers’ response) at the Cabinet meeting on 8 December 2016. |

# OUTLINE PROJECT PLAN

| Activity | Member Input Who is involved? Estimated time commitment | Officer Resource Who is involved? Estimated time commitment | When | Lead Person |
| --- | --- | --- | --- | --- |
| Scope session | All members invited – 2 hours on 30 August | Policy Team (Rebecka Steven and Shumailla Dar); Housing Team (Meghan Zinkewick-Peotti, Lynne Pennington and Jon Dalton) | 15 hours preparation 1 hour pre meeting 2 hour meeting | Prior to mtg 30 Aug 30 Aug | Rebecka Steven/ Meghan Zinkewich-Peotti |
| Finalise scope and obtain Overview and Scrutiny endorsement |  | Rebecka Steven/ Meghan Zinkewich-Peotti | 7 hours | Prior to 8 Sept | Rebecka Steven/ Meghan Zinkewich-Peotti |
| Research/Preparation Period/Desk top data gathering |  | Rebecka Steven/ Meghan Zinkewich-Peotti | 25 hours | For start October | Rebecka Steven/ Meghan Zinkewich-Peotti |
| Challenge Panel | Membership to be confirmed by Group offices; date to be confirmed with Chair for Challenge Panel. Challenge Panel to meet mid October. | Rebecka Steven | 4 hours | ASAP | Rebecka Steven |
| Collation and evaluation of data/evidence and draft report |  | Rebecka Steven/ Meghan Zinkewich-Peotti | 25 hours | Prior to 8 Sept | Rebecka Steven/ Meghan Zinkewich-Peotti |
| Challenge Panel members agree draft report | Members to provide comment | Rebecka Steven/ Meghan Zinkewich-Peotti | 5 hours |  | Rebecka Steven/ Meghan Zinkewich-Peotti |
| Early draft report to accountable manager for confirmation of factual accuracy |  | Rebecka Steven/ Meghan Zinkewich-Peotti Lynne Pennington/ Jon Dalton | 10 hours |  | Lynne Penningto/ Jon Dalton |
| Report submitted to Overview and Scrutiny |  | Rebecka Steven | 1hr |  |  |
| Challenge Panel’s presentation of report to CMT/DMT (if appropriate) | N/A | N/A | N/A | N/A | N/A |
| Final report of Group to O&S/Sub-Committee for approval (if necessary) | Chair to present to O&S Committee |  | 1hr |  |  |
| Consider if there is a need to publicise report findings |  | Rebecka Steven/ Meghan Zinkewich-Peotti Lynne Pennington/ Jon Dalton | 1 hr (plus any action agreed) |  |  |
| Final report published and referred to Executive for consideration (Cabinet/Portfolio Holder/Directorate – depending on issues/ recommendations) | Chair and Vice-Chair to present to Cabinet in December when Cabinet considers the officers response | Manize Talukdar | 1 hr |  |  |
| Evaluation of Challenge Panel process |  | Rebecka Steven | 5 hrs |  |  |
| Follow up/Monitoring of outcomes | PH to attend P&F 6-12 months post report | Rebecka Steven/Meghan Zinkewich-Peotti/ Lynne Pennington | 5 hours prep plus 1 hr attendance at meeting |  |  |
| TOTALS excluding scoping |  |  |  |  |  |

Contact: Rebecka Steven, Scrutiny team, Harrow Council