|  |  |
| --- | --- |
| WEST LONDON WASTE AUTHORITYAUDIT COMMITTEE  | 22 September 2017 |
| Report of the Treasurer and Managing Director |  |
|  **Risk Register** |
| SUMMARYThis report provides the Committee with an updated Risk Management Policy and details of the Authority’s updated Risk Register. |
|  |
| **RECOMMENDATION(S)**The Committee is asked to:-1. Approve the updated Risk Management Policy
2. Note the content of the Risk Register (Appendix 2)
 |

1. The Risk Management Policy sets out how the Authority manages risks. Last approved in 2015/16 this document has now been reviewed and updated (Appendix 1).
2. Only minor changes have been made to the policy statement and framework sections. A completely new section has also been added which:
	* describes the use of a risk register, a key tool for effective risk management and
	* defines the Authority’s risk appetite, low risk. This was a missing ISO3001 best practice policy item identified in an internal audit recommendation.
3. The corporate Risk Register is a formal document that is reviewed regularly by risk owners and is a standard agenda item discussed at WLWA Officer meetings which are held regularly, where risks and actions are considered and updated routinely.
4. The risks are grouped according to the widely used PESTLE framework - political, economic, social, technological, legislative and environmental risks. Each risk is reviewed individually with risk owners taking responsibility for updating the register and highlighting significant changes and new risks. At the end of the document you will find a matrix which helps Officers to score individual risks in terms of their probability and potential impactshould they crystallize.
5. **Appendix 2** provides the latest risk register which was updated at the latest Chief Officers’ meeting. In overall terms, the risk register identifies 20 Red and Amber risks facing the Authority and the mitigating actions. 18 of the risks have been mitigated to a Green status and there are 2 risks at Amber status.
6. **Financial Implications** – The financial element of each risk is considered as part of the impact score. The higher the score the larger the potential impact.
7. **Legal Implications** *–* There are no legal implications as part of this report.
8. **Impact on Joint Waste Management Strategy** *–* The risk register crosses all policies within the Joint Waste Management Strategy.

**Policy 7**: The West London Waste Authority and constituent Boroughs will seek to provide waste management services that offer good value, that provide customer satisfaction and that meet and exceed legislative requirements.

|  |  |
| --- | --- |
| Contact Officers | Jay Patel, Head of Finance 020 8825 9524jaypatel@westlondonwaste.gov.ukEmma Beal, Managing Director 020 8825 9488emmabeal@westlondonwaste.gov.ukIan O’Donnell, Treasurer 020 8825 5269Odonnelli@ealing.gov.uk  |

**Appendix 1**

**Risk Management Policy**

**Policy Statement**

One component of the Authority’s corporate governance framework is to manage risks effectively in order to make a positive contribution towards the achievement of the Authority’s corporate aims and objectives and to maximise the opportunities to achieve its vision, whilst obtaining assurances about the management of those risks.

The Authority is committed to the proactive management of key external and internal risks and actively promotes the principles of effective Risk Management throughout the organisation and its partner organisations. Effective partnership risk management allows the Authority to demonstrate a positive risk culture and improved outcomes, whilst improving its ability to deliver innovative and challenging projects.

Effective risk management is essential for both an organisation and its partners to achieve strategic objectives and improve outcomes for local people and for this to occur there needs to be strong leadership from Senior Officers and Members, clear strategies in place and trained and engaged staff.

The Authority’s Risk Management Policy and framework will apply best practice to the identification, evaluation and control of key risks and ensures that any residual risks are at an acceptable level. This will be achieved through:

* Adopting an effective and transparent corporate approach to proactive Risk Management by the Authority and the work of key external partners
* Integrating Risk Management into the operational and management practices and procedures of the Authority to promote a culture of risk awareness
* Providing information to support the Authority’s annual assurance statement, as to the effectiveness of the arrangements for risk management and internal control mechanisms in practice.

**Framework**

The Risk Management Framework provides the basis used to improve and strengthen governance and front-line service delivery throughout the Authority. The framework is described in the following bullet points:

* The Authority undertakes to promote and ensure that the management of risk is linked to the achievement of its priorities and service objectives and supports continuous improvement in service delivery and performance.
* The risk management approach will be appropriate to the size and scale of Authority operations and activities.
* Members and the senior management team own, lead and support risk management.
* Ownership and accountability are clearly assigned for the management of risks at all levels throughout the Authority. There is a commitment to embedding risk management into the Authority’s culture and organisational processes at all levels including corporate, project, operational and service.
* All Members and officers acknowledge and embrace the importance of risk management as a process, by which key risks and opportunities are identified, evaluated, managed and contribute towards good governance. This is reinforced through the delivery of appropriate training.
* Effective and transparent monitoring and reporting mechanisms are in place to continuously review the Authority’s exposure to, and management of, risks and opportunities. The effectiveness of these mechanisms are continually reviewed, updated and improved where opportunities arise.
* Open and inclusive processes are established and maintained by involving all those associated with the planning and delivery of services, including stakeholders and partners.
* Best practice systems for managing risk are used throughout the Authority, including mechanisms for monitoring and reviewing effectiveness against agreed standards and targets.
* Accountability to stakeholders is fully demonstrated through periodic progress reports and an annual assurance statement on the effectiveness of the Authority’s risk management framework. This includes the Annual Governance Statement.
* The policy statement and framework will be reviewed periodically as required, to ensure their continued relevance to the Authority.

**Risk register and risk appetite**

A key tool in the management of risk is the risk register. This identifies the key risks faced by the Authority and classifies them into the following categories:

* Political
* Economic
* Social
* Technological
* Legislative
* Environmental

The register is reviewed at all levels of management and makes an overall assessment (priority) of those risks based on scoring of the impact, likelihood and effect of mitigating actions. The assessment (priority) can be red, amber or green where green represents risks that have been largely mitigated and red risks are those which haven’t.

The Authority’s aim is to contain all risks within the green category (i.e. are largely mitigated). Essentially this demonstrates the Authority’s low risk appetite. However it should be noted that this may not be possible for all risks and where new risks emerge and mitigations are being put in place.

**Appendix 2**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Risk Area****"There is a risk that…"** | **Analysis of Risk "Which will result in…"** | **Type** | **Assessment of Risk** | **Management Actions Implemented or Planned (in bold)** | **Assessment of Risk** | **Responsible Officer** |
| **original score in brackets** | **after mitigations** |
| **Impact** | **Probability** | **Rating** | **Impact** | **Probabilit y** | **Rating** |
| Recycling targets and environmental legislation will weaken post Brexit | Unwanted facilities, expensive but sustainable methods of managing waste materials | Political | 4 (5) | 3 (4) | 12 (20) | Ongoing monitoring of proposals, respond to consultations and review as part of new contracts. Continue to attend CIWM events and monitor industry commentary and reiterate west London Boroughs intent to hit 50% target. | 4 | 1 | 4 | Managing Director |
| Authority decisions may be based on inaccurate or incomplete information | Inappropriate actions, unnecessary costs, challenge from an interested party and impact on reputation | Political | 5 | 2 | 10 | Scrutiny processes in place for reporting, reviewing and checking of any financial data by Officers. Borough officers consulted on all draft papers for financial and technical comment. Policy for handling conflicts of interest involving Members and/or Officers. | 5 | 1 | 5 | Managing Director |
| One or more of the waste treatment and disposal contracts will perform poorly or a single event will result in a need for business continuity planning. | Poor service to the Boroughs using the sites or needing material to be removed from site. Complaints about nuisance e.g. odour or pests. Increased cost of handling materials | Political | 5 | 2 | 10 | Ongoing review of contingency arrangements on each contract quarterly / annually asrequired. PPP contract used contingency arrangements during commissioning. Holding regular meetings with contractors and monitor KPIs as appropriate. Regular communication with Boroughs about service issues. Service monitoring and market information, reports on credit changes monitored. Credit checks and a review of accounts are routinely undertaken for new contracts and considered for contract extensions. | 5 | 1 | 5 | Contracts Manager |
| WLWA is not managed in accordance with policies and procedures or the policies and procedures are not robust. | Inappropriate decision making, failure to meet objectives and impact on reputation | Political | 5 | 2 | 10 | Internal management team meetings, Chief Officer’s meetings, Borough Partnership meetings and review of Authority papers. Audit Committee established with internal and external audit governance framework. Key performance indicators are reported to the Authority. Borough officers consulted on all draft papers for financial and technical comment. | 5 | 1 | 5 | Managing Director |
| WLWA financial processes are not robust | Internal fraud by an employee or contractor, bad information resulting in wrong decisions | Economic | 5 (4) | 2 | 10 (8) | Internal audit plan in place. Policies and procedures in place including arrangements for checking contracts and invoices. Segregation of duties between authorisation and checking of payments. Robust arrangements in place to control payments. Register of assets maintained. Processes in place for the monitoring of ad hoc contracts, contract management and negotiations. Whistle blowing policy. Standing Orders. 2015 Internal audit assurance Procurement fraud training rolled out in 2016 and declarations of interest extended to all staff involved in procurement. | 4 | 1 | 4 | Head of Finance and Performance |
| There will be unforeseen financial costs not covered by balances | An in-year levy to the Boroughs | Economic | 4 | 3 | 12 | Budget processes reviewed and monthly reporting demonstrating consistent performance. Budgets built from the bottom up with input and validation of data from boroughs. Boroughs nominate number of tonnes for PAYT budget for collected tonnes. Prudent levels of reserves are maintained to act as a buffer against any unforeseen risks and financial costs. Budget plan takes into account quantifiable risks. Where appropriate budgets are set with contingencies for identified risks. | 3 | 1 | 3 | Head of Finance and Performance |
| WLWA insurance cover will be insufficient | Inadequate cover to meet the costs of future claims, increasing difficulty in obtaining competitive quotes for waste industry facilities | Economic | 5 | 3 | 15 | There is an annual review with brokers and insurers to review adequacy of policies, claims history and premiums and options. Regular updates from insurer and broker advising of new policies. | 5 | 1 | 5 | Head of Finance and Performance |
| Funds (cash) are not managed effectively | Insufficient readily accessible cash to meet spending commitments resulting in financial penalties, legal claims and poor reputation. Poor rate of return on investments. | Economic | 4 | 4 | 16 | Cash planning in place. Processes in place to make payments swiftly, within minutes if necessary. Cash balances maintained to cover delays in borough transactions. 3 day turnaround time for calling down funding from investments. Opportunities to improve returns are reported to Chief Officers/Authority e.g. office procurement | 3 | 1 | 3 | Head of Finance and Performance |
| The contract payment mechanisms are not properly understood or ambiguous | Payment delays, under or overpayments or disputes | Economic | 5 (4) | 3 | 15 (12) | In-house checks of invoices by both operational and financial managers in place. Independent audit of contractor’s payment model. In depth contract knowledge of Sharpe Pritchard solicitors and PwC financial advisers. Monthly contract meetings, training and familiarisation with payment mechanisms | 5 (4) | 3 (2) | 15 (8) | Head of Finance and Performance |
| There will be fluctuations in material value due to recycling and raw material market forces | Uncontracted material streams may not be budgeted accurately, Falling scrap metal prices could lead to more abandoned vehicles for disposal, Boroughs cannot rely on a regular / known income from dry mixed recycling | Economic | 3 | 3 | 9 | Regular monitoring of all material markets and sharing information with Boroughs. **Action: Review arrangements for disposal of abandoned vehicles in Summer 2017/18.** | 3 | 2 | 6 | Contracts Manager |
| The loss of or absence of a key member of the team | Ineffective day to day management of the Authority, poor service delivery, contract management and long term planning | Economic | 3 | 3 | 9 | Recruitment policies, succession planning, cover/interim arrangements and other procedures limit impact on business continuity. New management structure largely in place | 2 | 2 | 4 | Managing Director |

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IT systems are insecure or suffer a major failure | Loss of data which we are obliged to report, or without which we cannot invoice or operate effectively | Economic | 4 (5) | 4 | 16 (20) | ICT service is delivered by LB Ealing and subject to a wide range of back-up and security measures including remote storage and performance to an agreed service level standards. An IT strategy is in place and IT requirements are regularly reviewed. LBE unable to provide service long term. New arrangements to replace LBE identified in IT report. Project resource and management to mitigate any risks. | 4 | 1 | 4 | Head of Finance and Performance |
| The waste flows are constantly changing | The contracted capacity does not match actual treatment requirement resulting in ineffective waste management arrangements | Social | 5 | 3 | 15 | Regular monitoring of waste flows and data patterns. Contracts with suitable flexibility/capacity. Liaison with boroughs for service changes, highlighting risks during the budget setting and budget monitoring. | 4 | 1 | 4 | Contracts Manager |
| The need for local facilities will be rejected by the planning process | Protracted and expensive planning applications, bad will from the local community and failure to ensure availability of ideal infrastructure | Social | 4 | 4 (5) | 16 (20) | Adopting appropriate project management approach will include early engagement with community liaison groups, robust site analysis and multiple options cost analysis. Careful selection well managed planning authorities. Discussions with neighboring WDAs | 4 | 3 | 12 | Contracts Manager |
| We are reliant on one member of staff for the access database | Being unable to administer/support ourcore IT system (developed by that member of staff), the Access waste data management system (used for checking invoices, submitting waste dataflow returns, providing management information). | Technological | 5 | 3 | 15 | Documented procedures allow continued day to day use of the system and the procurement of Opensky data management system with fully supported maintenance will mitigate this risk further. New system processes tested and working. Awaiting reports. | 4 | 2 | 8 | Head of Finance and Performance |
| WLWA Borough data is not being viewed holistically | A disjointed approach. Failure to capitalise on opportunity. Additional cost. A continuing disjointed approach. The Boroughs will fail to meet the 50% recycling composting target by 2010 | Technological | 5 | 3 | 15 | Data is viewed from an Authority perspective and ensures operations are effective for the Authority. However a more holistic view of data across all boroughs will facilitate better partnership working. Information needs documented. New project identified in Business plan. | 4 | 2 | 8 | Head of Finance and Performance |
| There will be a change in law relevant to our contracts | Unanticipated cost for the Authority | Legislative | 4 | 4 | 16 | Legislative changes are identified i.e. which affect EfW or transfer station operations, an incineration tax or change in classification to hazardous waste and are prepared for accordingly. Widp meetings are attended to gather from/share knowledge with other disposal authorities. Where possible costs will be built into the budgeting process or reported through budget monitoring and dealt with through reserves. | 4 | 2 | 8 | Contracts Manager |
| DCLG will challenge our HRRC provision or charging policy | Reputational damage, court action or a fine | Legislative | 3 | 3 | 9 | A Memorandum of Unerstanding (MoU) with boroughs and the availability of HRRC sites demonstrates performance of the statutory role. However the MoU expired in 2015 and charging policies across boroughs are disperate. New project identified in the business plan for HRRCs. | 1 | 2 | 2 | Operations Manager |
| Environmental damage will be caused by Authority or Contractor Activities | Increased cost of repair, potential fines, reputational damage | Environmental | 5 | 2 | 10 | Range of processes including internal daily and weekly monitoring. Review operations risks. Review procurement policy. Monitor contractor’s environmental performance and reporting. | 5 | 1 | 5 | Operations Manager |
| There will be a breach in Health & Safety at an Authority or Contractor site | Risk of injury to staff or public visitors to Authority sites | Environmental | 5 | 2 | 10 | Specialist Health and Safety Advice from LB Hounslow. 2015 Internal audit provided assurance. 2016/17 Action Plan considered and agreed with GMB. Monitor contractor’s health and safety performance and reporting. | 5 | 1 | 5 | Operations Manager |

