|  |
| --- |
|  |
| Brent and Harrow Suicide Prevention Action Plan 2019/20 – 2023/24 |
|  |



|  |
| --- |
| Brent and Harrow PH  11/29/2019 |

Contents

[Introduction 2](#_Toc26099774)

[Preventing Suicide in England – A national strategy 2](#_Toc26099775)

[Risk Factors and Data 4](#_Toc26099776)

[Brent and Harrow Priorities for 2019 – 2020 6](#_Toc26099777)

[Children and Young People 7](#_Toc26099778)

[Self-Harm 8](#_Toc26099779)

[Brent and Harrow Suicide Prevention Action Plan 11](#_Toc26099780)

[Action 1: Reduce the risk of suicide in key high-risk groups. 12](#_Toc26099781)

Action 2: Tailor approaches to improve mental health in all groups……………………………………………………………………………………………………………………………………….15

[Action 3: Reduce the access to means of suicide and tackle high frequency locations 17](#_Toc26099782)

[Action 4: Provide better information to those bereaved or affected by suicide 18](#_Toc26099810)

[Action 5: Support the media in delivering sensitive approaches to suicide and suicidal behaviour 19](#_Toc26099811)

[Action 6: Support research. Data collection and monitoring 20](#_Toc26099812)

[Partners 21](#_Toc26099813)

## Introduction

In 2018, there were 6,507 suicides registered in the UK, an age-standardised rate of 11.2 deaths per 100,000 population. This rate is significantly higher than that in 2017 and represents the first increase since 2013. Three-quarters of registered deaths in 2018 were among men (4,903 deaths). Despite low numbers of deaths overall, rates among the under 25s have generally increased in recent years, particularly 10 to 24-year-old females. The most common method of suicide in the UK was hanging, accounting for 59.4% of all suicides among males and 45.0% of all suicides among females[[1]](#footnote-1)..

## Preventing Suicide in England – A national strategy

Since publishing the national strategy for preventing suicide in 2012[[2]](#footnote-2), the Government has published several reports and strategies aimed at improving mental health and preventing suicide. The strategy mandated local authorities with the responsibility for leading local suicide prevention work in collaboration with local partners such as (but exclusive to) local Clinical Commissioning Groups (CCG), police, voluntary sector and the coroners office. Other national reports include the Five Year Forward View for Mental Health[[3]](#footnote-3) which set a national ambition in 2016 to reduce suicides by 10% by 2020/21.

The England strategy had two objectives which suicide prevention plans should reflect and work towards. These are:

* A reduction in the suicide rate in the general population in England; and
* better support for those bereaved or affected by suicide.

The strategy identified six key areas for action to support delivery of these objectives:

1: Reduce the risk of suicide in key high-risk groups

2: Tailor approaches to improve mental health in specific groups

3: Reduce access to the means of suicide

4: Provide better information and support to those bereaved or affected by suicide

5: Support the media in delivering sensitive approaches to suicide and suicidal behaviour

6: Support research, data collection and monitoring. An additional area of focus was added which included, reducing rates of self-harm.

Thrive LDN

Regionally in London during 2016-2018 the rate of suicide for all persons was 8.1 per 100,000[[4]](#footnote-4). 568 Londoners took their own lives in 2017, this equates to approximately 11 people every week. London currently has the lowest rate of suicide for the whole of England, although there is variation between the boroughs[[5]](#footnote-5). Thrive LDN are leading in developing a joined up approach to delivering suicide prevention activities. In addition to supporting Harrow to deliver Mental Health First Aid training to colleagues and professionals, they have also commissioned Papyrus UK to provide education to schools, colleges and London universities on suicide prevention through training workshops and organisational policy development. In addition to this, resources have been developed aimed at clinicians and primary care staff to reduce access to medication as a means of suicide to high risk groups.

Data sharing across London

Thrive LDN have also developed London’s first multi-agency information sharing hub, allowing vital information to be securely shared to enable effective bereavement support and the improvement of suicide prevention work throughout London. The data sharing hub will entail working with all councils to facilitate real time reporting enabling local councils to potentially have in-depth discussions and relationships with local officers of the Metropolitan Police and British Transport Police.

Zero Suicide London

Thrive LDN have partnered with the London Mayor and the Zero Suicide Alliance, to undertake a city wide movement to encourage 100,000 Londoners to take up a free training program to help anyone taking the training to be able to identify warning signs and feel comfortable having conversations about suicide. The free suicide prevention training can be found here: [Zero Suicide London](https://www.thriveldn.co.uk/campaigns/zerosuicideldn/)

Local Context**[[6]](#footnote-6)**.

* Brent and Harrow public health team are yet to undertake an audit with the local coroners office. Currently, Public Health teams cannot access the coroners to inform suicide numbers locally, due to significant changes across London. There will be seven new partnerships which will come together across London to implement and manage these new systems. As new partnerships, there is a responsibility for the partnership to implement new processes; collect a standardised dataset; ensure multi-agency input; undertake thematic learning; and provide routine support to

bereaved families. Hence, there is currently some uncertainty regarding the exact number , breakdown by age and gender, method of death and other such demographic data over time that is not available.

* Thrive LDN have now formalised the Pan-London Information Hub overseen and held by the London Metropolitan Police. The Hub will enable data and information to become available across all London boroughs by Sustainability and Transformation Partnership (STP). The data will support boroughs to look at patterns and interrogate a larger database to establish patterns, hot spots and themes. The process is, following a suspected suicide, data will be sent in the following order:
  + Category A Access: London Metropolitan Police, London Ambulance Service, British Transport Police and NHS Trusts (Mental Health)
  + Category B Access: A defined professional within the Local Authority. For Harrow and Brent this will be with the Public Health Teams.
* NHS NW London STP has received funding from NHS England and NHS Improvement to set up a service supporting people bereaved by suicide. The Postvention service is currently in development and will need to be set up by March/April 2020. Part of the development of the service will include capacity building by developing and rolling out training with services that offer bereavement counselling and support services.

## Risk Factors and Data

* In England and Wales, suicide is defined as deaths given an underlying cause of intentional self-harm or injury/poisoning of undetermined intent. Public Health England (PHE) Fingertips tool allows some insight into mental health and suicide data. This is collected by a combination of local CCG and Local Authority individual rates.
* Specific risk factors associated with suicide include the occurrence of common mental health disorders in people aged 16 and over in 2017 for Harrow CCG was 15.6% which was significantly better than the England benchmark of 16.9% and when compared to London which was 19.3%. These are estimated synthesised figures.
* Recent trends show that the occurrence of depression is on the increase. In 2017, Harrow CCG shows that there were 6.1% of people with depression on GP registers. Whilst the trend is increasing across NHS London region, these proportions are significantly better than NHS London which is 7.1%
* ONS data on the number of suicides recorded per year show that in the last seven years the numbers of suicide deaths have varied significantly between the boroughs. Figure 1 shows the absolute numbers of suicides between 2012 -2018 in Brent and Harrow.

**Figure 1. Number of absolute deaths per year in Brent and Harrow**

Source: ONS Suicides in the UK: 2018 Registrations

However, the rates of suicides within Brent and Harrow when compared to England and London rates, show little significant difference between 2016-2018. The current rate of suicides in Brent and Harrow is current lower than the England rates. See Table 1

**Table 1. Brent and Harrow Age Standardised rates of suicide per 100,000 compared with London and England**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | **Population** | **Age Standardised suicide rate per 100,000 population** | | | **Estimated Number of suicides per year** |
|  | **All** | **Male** | **Female** |  |
| *England[[7]](#footnote-7)* | 55,977,200 | 9.6 | 14.9 | 4.7 | - |
| *London* | 8,908,081 | 8.1 | 12.5 | 4.0 | - |
| Brent | 330,795 | 7.3 | 12.4 | 2.3 | 24 |
| Harrow | 250,149 | 6.4 | 9.0 | 3.6 | 16 |

Source: ONS Mid Year Population Estimates, PHE Mental Health and Wellbeing JSNA.

## Brent and Harrow Priorities for 2019 – 2020

Male Suicides

Male suicide has been described as a “silent epidemic”[[8]](#footnote-8). In the UK, suicide is the highest cause of death among men under the age 45. In Brent and Harrow, the rates of male suicides are higher than for females. One reason for the high rates seen in men, is that men are less likely to ask for help or express depressive or suicidal feelings[[9]](#footnote-9). Risk factors associated with male suicides include[[10]](#footnote-10):

* **Social-economic Factors** – Men are up to ten times more likely to end their lives by suicide than those in the highest social class from the most affluent areas.
* **Challenges in mid-life** – Considered the ‘buffer generation’ Men in mid-life now are part of the so-called ‘buffer’, men who are in their mid-life years find themselves caught between older, traditional fathers and younger, more progressive and individualistic sons.
* **Personality Traits** – Depression and other psychiatric illnesses contribute to suicide. Some personality traits and ‘mind-sets’ contribute to the development of suicidal thoughts, including the desire to be perfect; self-criticism; brooding; and having no positive thoughts about the future.
* **Masculinity** – Men compare themselves against a standard of masculinity and when there is a perception that this is not being met, this can lead to a sense of shame and defeat.

Recommendations for reducing male suicide rates from the Samaritans include:

1. Local suicide prevention strategies target men at the highest risk and consider gender and socio-economic disadvantage;
2. Prioritise interventions to mitigate stereotypes around masculinity and stigma around help-seeking;
3. Put in place ambitious policies to tackle the risk factors that can be linked to suicide risk in middle-aged men, including loneliness and alcohol misuse and
4. Roll out suicide awareness training programmes for GPs to improve diagnosis and signposting to services

## Children and Young People

Suicide in young people is rarely caused by one thing; it usually follows a combination of previous vulnerability and recent events.[[11]](#footnote-11) An estimated two hundred children a year lose their lives through completed suicide in the UK.[[12]](#footnote-12) Risk factors associated with suicides in children and young people are:

**Table xx Suicide risk factors for children and young people**

|  |  |  |
| --- | --- | --- |
| Behavioural disorders | Family breakdown | Mental health problems |
| Substance misuse | Rejection | Suicide in the family or a friend |
| Academic pressures | Bullying | Bereavement |
| Substance misuse | Childhood abuse | Sexual abuse |

The National Confidential Inquiry into Suicide and Homicide by People with Mental Illness produced a report in July 2017[[13]](#footnote-13) highlighting the impact of suicide methods found on the internet. Of the 922 suicides reviewed in England, they found suicide-related internet use in 26% of deaths in under 20s, and 13% of deaths in 20-24 year olds. This is the equivalent to 80 deaths per year.

The following table shows the crude rates of suicides for 10-34 year olds in Brent and Harrow compared to the England and London for the same age group. The rates of suicides in Brent and Harrow are similar to England rates however, slightly higher for the London region.

**Table 2. Crude rates for suicides over a 5 year period for 10-34 year olds in Brent and Harrow**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **England** | **London** | **Brent** | **Harrow** |
| Suicide crude rate for 10-34 year olds per 100,000 | 10.5 | 8.3 | 10.2 | 10.2 |

Source: PHE Fingertips

## Self-Harm

Nationally, self-harming in young people is not uncommon 10-13% of 15-16-year-olds have self-harmed in their lifetime[[14]](#footnote-14). Hospital admissions for self-harm in children have increased in recent years, with admissions for young women being much higher than admissions for young men. Self-harm is an expression of personal distress. There is a significant and persistent risk of future suicide following an episode of self harm.

Following an initial workshop with partners to discuss how suicide prevention within Harrow should be tackled, it was agreed that this years action plan would focus on Children and Young People. Young Harrow Foundation conducted a needs assessment of children and young people in Harrow, 15% of the target age (10-19 years) responded. Findings showed that young people in Harrow are struggling with mental health issues including self-harm and suicidal thoughts.

Data received from the Young Harrow Foundation has found that:

Out of 3870 CYP that answered the question around suicidal thoughts:

* 412 said they need support
* 312 said their close friends need support.
* These 2 numbers together says 17% of the CYP responding said there was a need around suicidal thinking.

Of the 412 that asked for the support themselves:

* 61% female
* 31% male
* 8% other

Of the 412 that asked for the support themselves:

* 53% also want support for self harm
* 49% want support to deal with bereavement
* Furthermore, there is a percentage of respondents in Harrow schools state that they would like support around suicidal thought. This ranges from as high as 16% of respondents.

The table below show emergency admissions for self harming in Brent and Harrow all ages including children and young people compared to England and London.

**Table 3. Self Harm Hospital Admissions**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **England** | **London** | **Brent** | **Harrow** |
| Emergency hospital admissions for intentional self-harm (standardised rate per 100,000) | 185.5 | 83.6 | 50.6 | 70.7 |
| Hospital admissions as a result of self-harm (10-24yrs) | 421.2 | 209.1 | 135.9 | 195.1 |

Source: Public Health England, Fingertips

Services which respond to self-harm are key to suicide prevention in children and young people. Recommendations for reducing suicide and self harming rates in children and young people include:

1. Support for young people who are bereaved, especially by suicide
2. Greater priority for mental health in colleges and universities
3. Housing and mental health care for looked after children
4. Mental health support for LGBT young people
5. Encourage online safety, especially for under 20s

## Brent and Harrow Suicide Prevention Action Plan

The national strategy preventing suicide in England: A cross-government outcomes strategy[[15]](#footnote-15) to save lives recommends that a multi-agency suicide prevention group alongside a local prevention action plan is collaboratively developed with local partners, drawing on local data and focusing on specific areas of action.

This action plan has six key areas:

1. Reduce the risk of suicide in key high-risk groups
2. Tailor approaches to improve mental health in all groups
3. Reduce the access to means of suicide and tackle high frequency locations
4. Provide better information to those bereaved or affected by suicide
5. Support the media in delivering sensitive approaches to suicide and suicidal behaviour
6. Support research, data collection and monitoring

The Action Plan has been developed in partnership with local organisations that either commission or deliver services related to mental and emotional health, suicide and bereavement support.

The Action Plan will focus on the tackling suicide rates in men and children and young people in Year 1 (2019-2020).

**Key:**

|  |  |
| --- | --- |
|  | Actions for 2019 -2020 |
|  | Proposed future actions 2021+ |

# Action 1: Reduce the risk of suicide in key high-risk groups.

Some groups of people are known to be at higher risk of suicide than the general population. The groups at high risk of suicide are:

* **young and middle-aged men;**
* women and girls
* people with a history of self-harm;
* people who misuse drugs and alcohol

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | **Objective** | **Action** | **Lead Agency** | **Due By** | **Joint Action** | **Progress 2019-20**  **(RAG)** |
| 1.1 | **Reduce the risk of suicides in men** | Ensure those working with men in different settings, receive suicide prevention training. | Public Health, Papyrus, Samaritans | April 2020 | Joint |  |
| 1.2 | Train primary care professionals to recognise signs of distress in men. | Public Health, Papyrus, Samaritans, COMPASS | Ongoing | Joint |  |
| 1.3 | Promote men’s mental health in community locations and traditional male settings | All Partners - Public Health, Men’s Health Forum, CALM, Sport/Football Club, Mental Health Foundation, Samaritans | Ongoing | Joint |  |
| 1.4 | Set up task and finish group to draw up proposals to increase help seeking by men. Includes focus on Eastern European men | Public Health, Samaritans, Sport/Football Club, CAB and Harrow Learn | February 2020 | Joint |  |
| 1.5 | **Reduce the risk of suicides and self-harm in children and young people** | Provide accessible suicide prevention information and materials to those in contact with children and young people | Young Harrow Foundation, Public Health | Ongoing | Joint |  |
| 1.6 | Improve access to early intervention programmes and support for children and young people | Young Harrow Foundation, WISH Centre, Molly Rose Foundation, KOOTH, COMPASS | Ongoing | Joint |  |
| 1.7 | Ensure that schools undertake online safety training. | Public Health | April 2020 | Joint |  |
| 1.8 | Offer all schools suicide prevention training and policy support. Including audit of policies in schools. | Public Health, Papyrus, Samaritans | Ongoing | Joint |  |
| 1.9 | Develop an online resource for parents to support self-harm and suicide | Harrow Young Foundation, CAMHS | December 2020 | Joint |  |
| 1.10 | Map and review referral pathways for CAMHS and increase suicide prevention training amongst staff | Harrow and Brent CCG, | 2021 -2024 | Joint |  |
| 1.11 | **Women and Girls** | Review the emerging evidence of women and girls self-harming and suicide rates in Brent and Harrow | Pan London Information Hub, Public Health, CDOP (STP) | 2021 – 2024 | Joint |  |
| 1.12 | Map services that support women and girls and embed self-harm and suicide prevention training | Voluntary Action, WISH Centre, Harrow Women’s Centre, Diwa Asian Women’s Network, Harrow CYP Safeguarding Board | 2021 – 2024 | Joint |  |
| 1.13 | Audit pathway for people attending Emergency Department following suicide or self-harm attempt to ensure clear support | NHS Acute Trusts  CNWL, Imperial NHS Trust and LNWHT | 2021-2024 | Joint |  |
| 1.14 | **People with a history of self harm** | Audit to investigate whether GP’s are contacted with details of suicidal/vulnerable person who have attended the Emergency Department | Brent and Harrow CCG’s | 2021-2024 | Joint |  |
| 1.15 | Review peer to peer support model for self-harm based on recommended good practice | WISH Centre, Public Health | 2021-2024 | Joint |  |

**Action 2: Tailor approaches to improve mental health in all groups**

As well as targeting high-risk groups, another way to reduce suicide is to improve the mental health of the population as a whole. This needs to include tailored measures for groups with particular vulnerabilities or problems with access to services.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | **Objective** | **Action** | **Lead Agency** | **Due By** | **Joint Action** | **Progress 2019-20**  **(RAG)** |
| 2.1 | **Reduce the risk of suicides in men** | Ensure GP’s understand and utilise mental health pathways and are able to sign post confidently to local services including social prescribing | Harrow and Brent CCG, Public Health | October 2020 | Joint |  |
| 2.2 | Public health to scope options for service user support of suicide prevention work | Public Health, Harrow Employment Services | April 2020 | Joint |  |
| 2.3 | Promote and deliver Mental Health First Aid Training for adults and Suicide Prevention training to NHS staff including ED staff and other allied professionals such as pharmacies | Public Health, Harrow and Brent CCG, NHS Trusts | Ongoing | Joint |  |
| 2.4 | **Reduce the risk of suicides and self-harm in children and young people** | Promote mental health first aid youth training and suicide prevention training to school staff | Public Health, Young Harrow Foundation | Ongoing | Joint |  |
| 2.5 | Link emerging actions from the ***Action for Change*** project in Harrow and Anna Freud ***Link Programme*** with the CCG to AP | Public Health, Young Harrow Foundation, Brent and Harrow CCG | April 2020 | Joint |  |
| 2.6 | Provide mental health advice and support to schools and early years settings including linking to Healthy Schools London and Healthy Early Years London programme. | Public Health, Healthy Schools and Healthy Early Years settings, HS: Team (Harrow Schools, Thriving Emotionally And Mentally) | Ongoing | Joint |  |
| 2.7 | **Reduce the risk of suicides and improve mental health in all groups in Brent and Harrow** | Work with local businesses to raise awareness of suicide and mental health by promoting Thrive LDN suicide prevention training and MHFA | Public Health, Harrow Economic development, Papyrus, Samaritans | Ongoing | Joint |  |
| 2.8 | Contribute and promote national campaigns on mental health and suicide prevention e.g. WMHD, Suicide Prevention Day | All partners | Ongoing | Joint |  |
| 2.9 | Build on the current joint working arrangements for co-morbidity by Harrow substance mis-use services and Harrow mental health | WDP, CNWL | Ongoing | Joint |  |
| 2.10 | Develop a peer mentoring /youth ambassadors programme to champion SP | All partners | Ongoing | Joint |  |
| 2.11 | Engage with charities and interfaith groups to improve understand and knowledge of suicide, linking actions to the Safeguarding Board Green Book | Voluntary Action Harrow, Public Health, Thrive LDN, Safeguarding Board | Ongoing | Joint |  |
| 2.12 | Work with universities and colleges to review their current arrangements for students in crisis | Brent Public Health, Universities and colleges. | Ongoing | Brent |  |
| 2.13 |  | Use contract mechanisms to ensure suicide awareness training is built into all contracts. All new contracts to include requirements for suicide prevention and intervention training | Brent and Harrow commissions, CCG commissioners, Safeguarding Board | 2021 -2024 | Joint |  |

# Action 3: Reduce the access to means of suicide and tackle high frequency locations

In order to tackle impulsive and opportunistic attempts of suicide is to reduce access to high-lethality means of suicide. As an example, evidence suggests that loss of life can be prevented when local agencies work together to discourage suicides at high-risk locations, including sites that temporarily become suicide hot-spots following a suicide death.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | **Objective** | **Action** | **Lead Agency** | **Due By** | **Joint Action** | **Progress 2019-20**  **(RAG)** |
| 2.1 | Reduce the risk of suicides in men | Identify high risk locations and review signposting at these locations |  | Ongoing | Joint |  |
| 2.2 | Reduce the risk of self-harm and suicide in children and young people | Contribute and support national campaigns that focus on reducing suicide and self-harm ideation | Public Health, Papyrus, Samaritans | Ongoing | Joint |  |
| 2.3 | Reduce the risk of suicides and improve mental health in all groups in Brent and Harrow | Feedback on actions undertaken from British Transport and Network Rail | BTP, Network Rail, Samaritans, Papyrus | 2021-2024 | Joint |  |
| 2.4 | Partnership group to engage with pharmacists to review safety of prescribing practices | Brent and Harrow CCG, Pharmacists, Public Health | 2021-2024 | Joint |  |
| 2.5 | Further work by CNWL to reduce access to means of suicide in inpatient facilities and reduce absconding among detained patients – may be useful | CNWL, Public Health | 2021-2024 | Brent |  |

# Action 4: Provide better information to those bereaved or affected by suicide

Effective and timely emotional and practical support for families bereaved or affected by suicide is essential to help the grieving process, prevent further or longer-term emotional distress and support recovery. It is important that GPs are vigilant to the potential vulnerability of family members when someone takes their own life. Providing better information for those bereaved means

* providing support that is effective and timely;
* having effective local responses in place to the aftermath of a suicide; and
* providing information and support for families, friends and colleagues who are concerned about someone who may be at risk of suicide.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | **Objective** | **Action** | **Lead Agency** | **Due By** | **Joint Action** | **Progress 2019-20**  **(RAG)** |
| 2.1 | **Reduce the risk of self-harm and suicide in children and young people** | Promote support offer to schools and siblings of those who have died by suicide | Public Health, Papyrus, Samaritans, Brent & Harrow Bereavement Care, Educational Psychology service, Brent and Harrow commissioning | April 2020 | Joint |  |
| 2.2 | **Reduce the risk of suicides and improve mental health in all groups in Brent and Harrow** | Promote NW London Postvention Service once support is established | All partners, NW London Partners | April 2020 | Joint |  |
| 2.3 | Utilise Help is at Hand z-card distribution in community settings, front line staff and primary care staff | All Partners | March 2020 | Joint |  |
| 2.4 | Explore potential for Survivors of Bereavement by Suicide (SOBS) Peer Support group to be set up in NWL | Public Health | 2021 -2024 | Joint |  |

# Action 5: Support the media in delivering sensitive approaches to suicide and suicidal behaviour

The action plan will support the two approaches to ensuring the media is sensitive to suicide and suicide behaviour. These are, promoting the responsible reporting and portrayal of suicide and suicidal behaviour in the media; and continuing to support the internet industry to remove content that encourages suicide and provide ready access to suicide prevention services.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | **Objective** | **Action** | **Lead Agency** | **Due By** | **Joint Action** | **Progress 2019-20**  **(RAG)** |
| 5.1 | **Reduce the risk of suicides and improve mental health in all groups in Brent and Harrow** | Ensure local media is aware of the Samaritans guidance on suicide reporting | All Partners | Ongoing | Joint |  |
| 5.2 | Support and promote national promotion days relating to mental health and suicide prevention. E.g. WMHD | All Partners | Goings | Joint |  |

# Action 6: Support research. Data collection and monitoring

* In order to inform the Action Plan, the group will:
  + build on the existing research evidence and other relevant sources of data on suicide and suicide prevention;
  + expand and improve the systematic collection of and access to data on suicides; and
  + monitor progress against the objectives of the national suicide prevention strategy.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | **Objective** | **Action** | **Lead Agency** | **Due By** | **Joint Action** | **Progress 2019-20**  **(RAG)** |
| 6.1 | **Reduce the risk of self-harm and suicide in children and young people** | Review and contribute to the emerging actions of the STP CDOP group | Harrow and Brent Safeguarding Board, Public Health | Ongoing | Joint |  |
| 6.2 | **Reduce the risk of suicides and improve mental health in all groups in Brent and Harrow** | Develop a detailed understanding of local suicide patterns. | Public Health | Ongoing | Joint |  |
| 6.3 | Contribute, receive and review information from the confidential data sharing Pan London Hub | NHS, London Ambulance Service, British Transport Police, Metropolitan Police, Thrive LDN, Brent and Harrow Public Health | Ongoing | Joint |  |

## Partners

List of partners signed up to the Brent & Harrow Suicide Prevention Action Plan

|  |  |
| --- | --- |
| Brent Contributors | Harrow Contributors |
| Public Health | Public Health |
|  | Harrow Council Commissioning – Children and Young People |
|  | Harrow Educational Psychology service |
|  | Marlborough Primary School |
|  | Public Health Commissioner |
|  | Harrow Bereavement Care |
|  | WDP – Harrow Adult Substance Mis-Use Service |
| CNWL | CNWL |
|  | Harrow CCG (Children and Young People Commissioning) |
| Brent CCG | Harrow CCG |
| Papyrus | Papyrus |
| Brent Samaritans | Harrow Samaritans |
|  | Voluntary Action Harrow |
|  | Harrow Council Housing |
|  | Harrow Young Foundation |
| CAMHS Urgent Care Team (Harrow & Brent Hub) | CAMHS Urgent Care Team (Harrow & Brent Hub) |
| Network Rail | Network Rail |
| Metropolitan Police | Metropolitan Police |

1. ONS Suicides in the UK: 2018 Registrations. Available

   <https://www.ons.gov.uk/peoplepopulationandcommunity/birthsdeathsandmarriages/deaths/bulletins/suicidesintheunitedkingdom/2018registrations> [↑](#footnote-ref-1)
2. HMG and DH Preventing suicide in England. A cross-government outcomes strategy to save lives (2012) Available here: <https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/430720/Preventing-Suicide-.pdf> [↑](#footnote-ref-2)
3. NHS The Five Year Forward View for Mental Health. A report from the independent Mental Health Taskforce to the NHS in England (2016). Available here: <https://www.england.nhs.uk/wp-content/uploads/2016/02/Mental-Health-Taskforce-FYFV-final.pdf> [↑](#footnote-ref-3)
4. Public Health England Fingertips Tool. Suicide Prevention Profiles. Found here: <https://fingertips.phe.org.uk/profile-group/mental-health/profile/suicide/data#page/0/gid/1938132828/pat/6/par/E12000007/ati/102/are/E09000015> [↑](#footnote-ref-4)
5. Thrive LDN Suicide Prevention. Found here: <https://www.thriveldn.co.uk/core-activities/suicide-prevention/> [↑](#footnote-ref-5)
6. Public Health England Fingertips Tool. Common Mental Health Disorders. <https://fingertips.phe.org.uk/profile-group/mental-health/profile/common-mental-disorders/data#page/0/gid/8000041/pat/46/par/E39000018/ati/165/are/E38000004/iid/91841/age/168/sex/4> [↑](#footnote-ref-6)
7. ONS 2018 Mid Year estimates. Available here: <https://www.ons.gov.uk/peoplepopulationandcommunity/populationandmigration/populationestimates/datasets/populationestimatesforukenglandandwalesscotlandandnorthernireland> [↑](#footnote-ref-7)
8. F. Baffour(2018). The British Psychological Society online article. Male Suicide: A Silent Epidemic. Online and available here: <https://www.bps.org.uk/blogs/dr-funke-baffour/male-suicide-silent-epidemic> [↑](#footnote-ref-8)
9. Ibid8 [↑](#footnote-ref-9)
10. Samaritans and Network Rail (2012). Men and Suicide. Why it’s a social issue. Available here: <https://www.samaritans.org/about-samaritans/research-policy/middle-aged-men-suicide/> [↑](#footnote-ref-10)
11. Suicide by children and young people. National Confidential Inquiry into Suicide and Homicide by People with Mental Illness (NCISH). Manchester: University of Manchester, 2017. [↑](#footnote-ref-11)
12. Papyrus. Building suicide-safer schools and colleges: a guide for teachers and staff. 2018. <https://tinyurl.com/yxj36j9p> [↑](#footnote-ref-12)
13. Ibid11  Available here: <https://www.hqip.org.uk/wp-content/uploads/2018/02/8iQSvI.pdf> [↑](#footnote-ref-13)
14. Department of Health, No Health Without Mental Health: A cross-government mental health outcomes strategy for people of all ages (2 February 2011). Available here: <http://www.dh.gov.uk/prod_consum_dh/groups/dh_digitalassets/documents/digitalasset/dh_124058.pdf> [↑](#footnote-ref-14)
15. Department of Health. Suicide Prevention Strategy for England (2012). <https://www.gov.uk/government/publications/suicide-prevention-strategy-for-england> [↑](#footnote-ref-15)