## Slide 1
Harrow Winter Improvement Plan
and System Pressures Metrics
January 2024

## Slide 2: Winter Improvement Plan
The action plan on the three following slides was developed by the Harrow Borough Based Partnership to prepare the system for the Winter Period.
The planned actions aim to support the provision of high quality care in the community, the prevention of admission to hospital and safe and efficient discharge to the community once patients’ acute needs have been met.
The actions that the system committed to complete in 2023 have been delivered and it is expected that those scheduled for January will also be completed as planned.

## Slide 3: Winter Improvement Plan Actions (1/3)
Action | Target impacted | Status | 30 Nov | 31 Dec | 31 Jan | 28 Feb | 31 Mar
Implement Harrow Bridging Service | Reduce % of patients without C2R, not discharged | Spec and procurement complete. Service commenced 16/11/23. Service accepting all referrals from MDT but spare capacity – review of potential to manage wider cohort of patients. | Commenced |  |  |  | 
Harrow Multi-Agency Admission Avoidance Summit | Reduce ASC NEL admissions | Multi-agency summit took place 09/11/23. | Action plan agreed. |  |  |  | 
Action plan to improve review of children attending hospital due to asthma | Reduce ASC NEL admissions | Task and finish group established. Data analysis complete. | Action plan agreed. |  |  |  | 
Implement local escalation processes for discharge delays as described in the winter plan | Reduce % of patients without C2R, not discharged | Twice daily Discharge Hub / ASC MDTs established 09/10/23. Three times weekly PL DTOC reporting to Partnership Leaders, | In place |  |  |  | 
Launch ‘Radar’ function of Harrow Frailty Dashboard to identify rising risk patients | Reduce ASC NEL admissions | Risk stratification radar launched 02/11 for use by primary care to identify patients with rising risk of deterioration. | Complete |  |  |  | 

## Slide 4: Winter Improvement Plan Actions (2/3)
Action | Target impacted | 31 October | 30 November | 31 December | 31 January | 28 February
Implement 2023/24 winter wellness scheme: Deliver Make Every Contact Count winter programme | Reduce ASC NEL admissions | Public Health and Voluntary Action Harrow training programme started 06/11 | Ongoing |  |  | 
Review pathway for discharge of patients in rehabilitation units | Reduce % of patients without C2R, not discharged | MDT established. P2 NCTRs reducing. | In place. |  |  | 
Review processes for admissions from and discharge to care homes | Reduce % of patients without C2R, not discharged Reduce ASC NEL admissions |  | Review complete 30/11 | Finalise pathway between care homes and LNW virtual wards. | Draft discharge pathway and SOP TBC 08/01/23. | Trusted assessor model to be developed.
Improve process for discharging patients from CNWL mental health beds to reduce delays | Reduce % of patients without No Criteria to Remain, not discharged | Adult social care review pathway accelerated, Currently no patients whose discharge is delayed (03/01/23) |  |  |  | 
Secure access to clinical records across CNWL and Drug and Alcohol service provider. | Prevent admissions to secondary inpatient care | CNWL data available to D&A team. Further work to resolve IG issues for sharing of Drug and Alcohol Service data. |  |  |  | 

## Slide 5: Winter Improvement Plan Actions (3/3)
Action | Target impacted | 31 October | 30 November | 31 December | 31 January |  | 28 February | 31 March
LNWHT winter inpatient beds Phase 1: open 33 beds up across NPH and EH from October Phase 2: open NPH SAU level 4 from November Phase 3: open 32 NPH AMU modular beds from March |  | Phase 1: 23 of 33 beds open | Phase 2: open 14 NPH SAU level 4 trollies |  | Phase 1: 33 of 33 beds open |  |  | Phase 3: 32 NPH AMU modular beds open
Digital solutions to support flow and discharges to improve monitoring of patient flow actions through Timely Care Hub and Optica | Reduce % of patients without C2R, not discharged | Continued working with CCS to develop the digital tools to interface with Cerner |  |  |  |  |  | 
Increase daily discharges via NPH and EH Discharge Lounges | Reduce % of patients without C2R, not discharged | Daily process in place to review all discharges for suitability Daily review of confirmed and potential discharges with Divisional Teams |  |  |  |  |  | 
REACH: 12 week pilot for ED Consultant to triage LAS call-in anticipation of preventing conveyance by offering A&G or diverting call to SPA for SDEC/other specialty alternatives. REACH will operate M-F, 1000-1800 | Reduce ASC NEL admissions | 12 week pilot commenced as of 11 Oct |  |  |  |  |  | 
Increase conversion NPH | Same day emergency care: Reduced waits to be seen in ED Rapid Access Unit NPH |  | Converting NPH CDU D Bay to increase access to non-specific chest pain, needlestick injuries, hyperkalaemia and post CT KUB |  |  |  |  | 

## Slide 6: Harrow System Pressures Metrics
The data in the following slides reflects the system position just prior to Christmas, a time when demand on health and care services is usually relatively low.
Further data will become available between the submission of this report and the meeting of the Health and Wellbeing Board, which will cover the first week after New Year, when the health and care system usually experiences a surge in demand.
Early indications (Wednesday 3rd January) are that the combination of a surge in demand and the impact of the Junior Doctors’ Strike is having a severe impact on services.
A briefing on the latest position will be prepared for discussion by the Board.
The final slide contains a summary of some longer term trends that have emerged in 2023. These include a significant increase in the number of A&E attendances and a very large increase in the number of people receiving social care support after discharge from hospital.

## Slide 7: Harrow System Pressures Metrics (1/2)
 | System Indicators | Cohort | Frequency | Data Period | Current Period | Previous Period | Context | 
Success of Prevention Measures |  |  |  |  |  |  |  | 
1 | Autumn Campaign - Covid vacc uptake | Harrow | Weekly | WE 24/12 | 34.84% | 34.85% | NWL uptake | 27.0%
2 | Autumn Campaign - Flu vacc uptake | Harrow | Weekly | WE 21/12 | 38.15% | 37.85% | NWL uptake | 33.3%
Demand pressure |  |  |  |  |  |  |  | 
6 | AED Attends | NPH | Weekly | WE 24/12 | 2248 | 2246 | Avg over last winter (Oct 22 - Apr 23) | 2,139
7 | AED Attends Paeds | NPH | Weekly | WE 24/12 | 409 | 444 | Avg over last winter (Oct 22 - Apr 23) | 546
8 | UTC Attends | NPH | Weekly | WE 24/12 | 1432 | 1582 | 3 mth avg | 1,314
9 | AED Emergency Admissions | NPH | Weekly | WE 24/12 | 667 | 711 | Avg over last winter (Oct 22 - Apr 23) | 642
10 | Community/District Nursing - Visits completed (in hours) | Harrow | Weekly | WE 23/12 | 1,673 | 1,654 | Avg over last winter (Oct 22 - Apr 23) | 2,321
11 | Community/District Nursing - Rostered staff (in hours) | Harrow | Weekly | WE 23/12 | 1,558 | 1,455 | Avg over last winter (Oct 22 - Apr 23) | 1,843
12 | No hospital discharges in month that required social care input | Harrow | Monthly | Oct-23 | 147 | 147 | Mar ‘20 Avg | 178
13 | No of patients being worked with by social care | Harrow | Monthly | Oct-23 | 337 | 337 | Mar ‘20 Avg | 91
14 | MH Liaison AED Referrals | Harrow | Weekly | WE 24/12 | 63 | 73 | Avg over last winter (Oct 22 - Apr 23) | 33
15 | MH Liaison AED Referrals - 1 hour response | Harrow | Weekly | WE 24/12 | 90.2% | 83.3% | Avg over last winter (Oct 22 - Apr 23) | 62%
16 | MH Liaison Ward referrals | Harrow | Weekly | WE 24/12 | 34 | 33 | Avg over last winter (Oct 22 - Apr 23) | 60
17 | MH Liaison Ward referrals - 24 hour response | Harrow | Weekly | WE 24/12 | 72.2% | 63.6% | Avg over last winter (Oct 22 - Apr 23) | 85%
18 | Rapid Response - Visits completed (in hours) | Harrow | Weekly | WE 23/12 | 200 | 360 | Avg over last winter (Oct 22 - Apr 23) | 330
19 | Rapid Response - Rostered staff (in hours) | Harrow | Weekly | WE 23/12 | 147.75 | 391 | Avg over last winter (Oct 22 - Apr 23) | 390
20 | No of referrals to drug and alcohol service |  |  |  |  |  |  | 
21 | Urgent referrals to drug and alcohol service |  |  |  |  |  |  | 
22 | No of referrals to Housing for homeless patients with MH issues |  |  |  |  |  |  | 
23 | Urgent referrals to Housing for homeless patients with MH issues |  |  |  |  |  |  | 
24 | People contacting LA about Damp / Mould | Harrow | Monthly | Nov-23 | 104 | 69 | 3 mth avg | 76
26 | Covid Related 111 Calls | Harrow | Weekly | WE 24/12 | 147 | 110 | Avg over last winter (Oct 22 - Apr 23) | 69

## Slide 8: Harrow System Pressures Metrics (1/2)
 | System Indicators | Cohort | Frequency | Data Period | Current Period | Previous Period | Context | 
Pathway Efficiency |  |  |  |  |  |  |  | 
27 | Delayed Transfers of Care – Community Beds (P2) | Harrow | Weekly | WE 26/12 | 11 | 10 | 4 wk avg | 9
28a | Delayed Transfers of Care - Pathway 0 | NPH - Harrow | Weekly | WE 26/12 | 7 | 7 | 4 wk avg | 15
28b | Delayed Transfers of Care - Pathway 1 | NPH - Harrow | Weekly | WE 26/12 | 12 | 16 | 4 wk avg | 8
28c | Delayed Transfers of Care - Pathway 2 | NPH - Harrow | Weekly | WE 26/12 | 8 | 8 | 4 wk avg | 5
28d | Delayed Transfers of Care - Pathway 3 | NPH - Harrow | Weekly | WE 26/12 | 5 | 2 | 4 wk avg | 4
 | Delayed Transfers of Care Total | NPH - Harrow | Weekly | WE 26/12 | 32 | 33 | 4 wk avg | 37
28e | Delayed Transfers of Care - Unstated Pathway | NPH - Harrow | Weekly | WE 26/12 | 3 | 2 | 4 wk avg | 11
39 | Community Equipment Delays | Harrow | Monthly |  |  |  |  | 
40 | Enhanced Frailty service - Current Caseload | Harrow | Monthly | Nov-23 | 189 | 195 | 6 mth avg | 192
41 | Enhanced Frailty service - Step ups | Harrow | Monthly | Nov-23 | 76 | 65 | 6 mth avg | 69
42 | Enhanced Frailty service - Step down | Harrow | Monthly | Nov-23 | 64 | 72 | 6 mth avg | 66
System Stress |  |  |  |  |  |  |  | 
56 | Hospital Capacity Status | NPH | Weekly | WE -26/12 | Green | FCP | % of weeks FCP over last winter (Oct 22 - Apr 23) | 83%
57 | 12 Hour AED Waits | NPH | Weekly | WE -24/12 | 187 | 198 | Avg over last winter (Oct 22 - Apr 23) | 313
58 | LAS Handovers - No. of 60 min Breaches | NPH | Weekly | WE -24/12 | 1 | 18 | Avg over last winter (Oct 22 - Apr 23) | 103
59 | Community/District Nursing - No. of visits deferred once | Harrow | Weekly | WE -23/12 | 15 | 60 | Avg over last winter (Oct 22 - Apr 23) | 4
60 | Community/District Nursing - No. of visits deferred more than once | Harrow | Weekly | WE -23/12 | 0 | 0 | Avg over last winter (Oct 22 - Apr 23) | 1
61 | Rapid Response - No. of referrals with a 2 hour response time | CLCH | Weekly | WE -23/12 | 58 | 80 | Avg over last winter (Oct 22 - Apr 23) | 69
62 | Rapid Response - Initial visits not completed within 2 hours | CLCH | Weekly | WE -23/12 | 2 | 10 | Avg over last winter (Oct 22 - Apr 23) | 2
63 | Rapid Response - No. of referrals rejected due to capacity | CLCH | Weekly | WE -23/12 | 0 | 0 | Avg over last winter (Oct 22 - Apr 23) | 0
64 | Community Services Sickness Absence | Harrow | Weekly | WE -23/12 | 1.1% | 2.3% | Avg over last winter (Oct 22 - Apr 23) | 3.9%

## Slide 9: Summary of Key Issues in Longer Term Trends
System | Indicator (s) | Lead Provider | Current Position (See metrics schedues for details) | Longer-term Trend
Demand for Unscheduled Care | Accident and Emergency Department Attendances / Non-elective admissions at NPH | Northwick Park Hospital (LNWUHT) | Both A&E attendances and non-emective admissions are currenty above /the average for ast winter. | A&E admissions now average 2,100 per week, a level that, pre-Covid woud have been a peak in activity. Non-elective admissions average approximately 600 per week.
Demand for Unscheduled Care | 12 Hour A&E waits v LAS 60 minute Handover Delays | Northwick Park Hospital (LNWUHT) | There were 397 12 Hour A&E waits last week compared to an average last winter of 313. There were no 60 minute LAS handover delays compared to an average last winter of 103. | LAS managing patients at the hospital in stationary ambulances when capacity was not available in A&E resulted in long handover delays and poor LAS response times. This approach changed in June 2023 and the result has been very few handover delays and a sharp increase in 12 hour waits in A&E.
Hospital Discharge | Hospital Discharges | Northwick Park Hospital (LNWUHT) | Discharges in most recent week from NOPW ere 655 against an average over the last year of 503. | Since August discharges have been above 600, compared to an average for 12 months of 503, peaking at 746 earlier in December.
Social Care Demand | Patients discharged needing social care support v those remaining on social care caseload | LB Harrow Adult Social Care | The number of patients leaving hospital requiring social care support in October (147) was lower than last year’s winter average (178). Thr average number of discharged patients in September and October receiving support from social care was 425, compared to last winter’s average of 298. | Although the number of patients discharged from hospital requiring social care support has not increased since 2019/20, the number continuing to receive support in 2022/23 and 2023/24 has increased from fewer than 100 to approximately 300. Although the full explanation of this change will be complex, the move to earlier discharge is a significant factor in this increase in demand for social care.